## Sheet1
Label | Description
Created by checklistguro.com
Start (START) | Start of the Workflow/Process
1. Retrieve Product Backlog (ENTRY_GET) | Fetch all unprioritized user stories from the Product Backlog data model.
2. Set Sprint Status to 'Planning' (ENTRY_UPDATE) | Update the current Sprint entry status to 'Planning' to lock the backlog for the session.
3. Create Backlog Refinement Task (TASK_CREATE) | Assign a task to the Product Owner to review and refine high-priority stories.
4. Get Team Capacity (ENTRY_GET) | Retrieve available hours/points for all team members from the Resource model.
5. Calculate Total Team Capacity (ENTRY_AGGREGATE) | Sum the available hours/points of all team members for the upcoming sprint duration.
6. Fetch Priority Stories (ENTRY_GET) | Get stories from the Backlog that have been marked as 'Ready for Sprint'.
7. Estimate Story Point Load (CALCULATION) | Calculate the total sum of story points for all selected stories to compare against capacity.
8. Create Sprint Planning Meeting (TASK_CREATE) | Create a task for the Scrum Master to facilitate the planning session with the team.
9. Create Sprint Entry (ENTRY_CREATE) | Generate a new record in the Sprint data model with the defined start and end dates.
10. Assign Stories to Sprint (ENTRY_UPDATE) | Update the selected backlog stories to link them to the newly created Sprint ID.
11. Create Task Breakdown (TASK_CREATE) | Create sub-tasks for each story to define technical implementation steps.
12. Verify Sprint Load Ratio (ENTRY_AGGREGATE) | Calculate the ratio of Total Story Points vs. Total Team Capacity to check for over-commitment.
13. Finalize Sprint Scope (ENTRY_UPDATE) | Update the Sprint entry status to 'Active' and lock the scope.
14. Notify Team of Sprint Start (EMAIL) | Send an email to all team members containing the Sprint goal and the link to the Sprint board.
15. Generate Sprint Commitment Report (REPORT_CREATE) | Create a report showing the list of committed stories and the total workload vs capacity.
End (END) | End of the Workflow/Process