## 6a410ec38d045fc590b65e89
Label	Description

Created by checklistguro.com

Start (START)	Start of the Workflow/Process
1. Retrieve Equipment Master List (ENTRY_GET)	Fetch all machinery and assets from the Equipment Data Model that are due for maintenance.
2. Create Shutdown Project Entry (ENTRY_CREATE)	Initialize a new Shutdown Plan entry in the Maintenance Projects data model with a specific date range.
3. Calculate Total Estimated Parts Cost (ENTRY_AGGREGATE)	Sum the estimated costs of all required spare parts identified in the maintenance requirements.
4. Assign Safety Audit Task (TASK_CREATE)	Create a task for the Safety Officer to review the shutdown risk assessment.
5. Update Shutdown Budget (ENTRY_UPDATE)	Update the 'Total Estimated Cost' field in the Shutdown Project entry with the aggregated parts cost.
6. Calculate Resource Gap (CALCULATION)	Calculate the difference between 'Required Man-hours' and 'Available Man-hours' from the Resource Plan.
7. Create Contractor Procurement Task (TASK_CREATE)	Create a task for the Procurement Manager to issue RFPs for external labor services.
8. Get Available Technician Schedule (ENTRY_GET)	Retrieve the availability data for the maintenance team during the shutdown window.
9. Create Critical Path Schedule Task (TASK_CREATE)	Create a task for the Maintenance Planner to build the hour-by-hour shutdown sequence.
10. Create Spare Parts Order (ENTRY_CREATE)	Create entries in the Purchase Order data model for all required critical components.
11. Notify Stakeholders of Shutdown Dates (EMAIL)	Send an email to Department Heads regarding the confirmed shutdown window and expected downtime.
12. Update Maintenance Schedule Status (ENTRY_UPDATE)	Update the status of the Shutdown Project to 'Planned' once the schedule is finalized.
13. Generate Shutdown Readiness Report (REPORT_CREATE)	Generate a summary report showing completed tasks, budget vs. actual, and identified risks.
14. Alert Emergency Response Team (SMS)	Send an SMS alert to the emergency response lead to ensure standby availability.
15. Remove Cancelled Work Orders (ENTRY_DELETE)	Delete entries from the Work Order data model that were identified as non-critical and deferred to next year.
End (END)	End of the Workflow/Process