## 6a410f4a8d045fc590b66056
Label	Description

Created by checklistguro.com

Start (START)	Start of the Workflow/Process
1. Fetch Project Budget Details (ENTRY_GET)	Retrieve the total allocated budget and current spending data from the Project Data Model.
2. Fetch All Expense Entries (ENTRY_GET)	Retrieve all individual expense records associated with the current Project ID.
3. Calculate Total Actual Spend (ENTRY_AGGREGATE)	Sum the 'Amount' property of all retrieved Expense Entries to determine total expenditure to date.
4. Calculate Remaining Budget (CALCULATION)	Subtract the Total Actual Spend from the Total Allocated Budget to find the remaining balance.
5. Calculate Budget Variance Percentage (CALCULATION)	Calculate the percentage difference between the planned budget and the actual spend.
6. Determine Budget Status (CALCULATION)	Evaluate if the variance exceeds a predefined threshold (e.g., if variance > 10%, flag as 'Over Budget').
7. Update Project Financial Status (ENTRY_UPDATE)	Update the 'Financial Health' field in the Project Data Model based on the calculated variance.
8. Create Budget Alert Task (TASK_CREATE)	Assign a task to the Project Manager if the budget variance exceeds the threshold.
9. Create Re-forecasting Task (TASK_CREATE)	Assign a task to the Finance Controller to review and adjust project forecasts if over budget.
10. Create Budget Exception Log (ENTRY_CREATE)	Create a new entry in the 'Budget Alerts' data model to document the specific instance of overspending.
11. Notify Stakeholders of Overrun (EMAIL)	Send an email to the Project Sponsor and Finance Department regarding the budget alert.
12. Generate Monthly Cost Report (REPORT_CREATE)	Generate a structured report summarizing all expenses, variances, and remaining funds for the current period.
13. Update Forecasted End-of-Project Cost (ENTRY_UPDATE)	Update the 'Projected Total Cost' field in the Project Data Model based on current burn rate.
14. Urgent Budget Alert SMS (SMS)	Send an SMS notification to the Project Manager for critical budget breaches (e.g., >20% over budget).
15. Remove Duplicate Expense Entry (ENTRY_DELETE)	Delete an error-prone or duplicate expense entry identified during the reconciliation process.
End (END)	End of the Workflow/Process