## Sheet1
Label | Description
Created by checklistguro.com
Start (START) | Start of the Workflow/Process
1. Fetch Project Budget Details (ENTRY_GET) | Retrieve the total allocated budget and current spending data from the Project Data Model.
2. Fetch All Expense Entries (ENTRY_GET) | Retrieve all individual expense records associated with the current Project ID.
3. Calculate Total Actual Spend (ENTRY_AGGREGATE) | Sum the 'Amount' property of all retrieved Expense Entries to determine total expenditure to date.
4. Calculate Remaining Budget (CALCULATION) | Subtract the Total Actual Spend from the Total Allocated Budget to find the remaining balance.
5. Calculate Budget Variance Percentage (CALCULATION) | Calculate the percentage difference between the planned budget and the actual spend.
6. Determine Budget Status (CALCULATION) | Evaluate if the variance exceeds a predefined threshold (e.g., if variance > 10%, flag as 'Over Budget').
7. Update Project Financial Status (ENTRY_UPDATE) | Update the 'Financial Health' field in the Project Data Model based on the calculated variance.
8. Create Budget Alert Task (TASK_CREATE) | Assign a task to the Project Manager if the budget variance exceeds the threshold.
9. Create Re-forecasting Task (TASK_CREATE) | Assign a task to the Finance Controller to review and adjust project forecasts if over budget.
10. Create Budget Exception Log (ENTRY_CREATE) | Create a new entry in the 'Budget Alerts' data model to document the specific instance of overspending.
11. Notify Stakeholders of Overrun (EMAIL) | Send an email to the Project Sponsor and Finance Department regarding the budget alert.
12. Generate Monthly Cost Report (REPORT_CREATE) | Generate a structured report summarizing all expenses, variances, and remaining funds for the current period.
13. Update Forecasted End-of-Project Cost (ENTRY_UPDATE) | Update the 'Projected Total Cost' field in the Project Data Model based on current burn rate.
14. Urgent Budget Alert SMS (SMS) | Send an SMS notification to the Project Manager for critical budget breaches (e.g., >20% over budget).
15. Remove Duplicate Expense Entry (ENTRY_DELETE) | Delete an error-prone or duplicate expense entry identified during the reconciliation process.
End (END) | End of the Workflow/Process