## 6a390e3f5a1e7cf130c0ca18
Label	Value	Notes

Created by ChecklistGuro (https://checklistguro.com)

Pre-Installation & Planning (STEP)
Project Number (SELECTION options: Enter Project Number)
Scheduled Start Date (DATE)
Review of Approved Shop Drawings (TEXT)
Relevant Permits Obtained? (SELECTION options: Building Permit, Environmental Permits, Other Permits)
Cladding System Type (SELECTION options: Brick, Siding (Vinyl, Wood, Fiber Cement), Metal Panels (Aluminum, Steel), Other)
Site Access & Safety Plan Review (TEXT)
Expected Duration of Cladding Installation (days) (NUMBER)
Upload Relevant Drawings/Specifications (UPLOAD)

Substrate Preparation (STEP)
Sheathing Thickness (inches) (NUMBER)
Framing Spacing (inches) (NUMBER)
Sheathing Type (SELECTION options: Plywood, OSB, Cement Board, Other)
Description of any substrate modifications/repairs (TEXT)
Substrate Leveling Required? (SELECTION options: Yes, No)
Photos of Substrate Condition (before work) (UPLOAD)
Date Substrate Preparation Completed (DATE)
Details of any sealant/adhesive applied and manufacturer details (TEXT)

Material Receipt & Storage (STEP)
Quantity Received (per material type) (NUMBER)
Quantity Ordered (per material type) (NUMBER)
Material Condition Upon Arrival (SELECTION options: Excellent, Good, Fair, Damaged)
Description of any Damage/Discrepancies (TEXT)
Photographs of Received Materials (if applicable) (UPLOAD)
Material Storage Location (SELECTION options: Designated Storage Area, Temporary Site Location, Other (Specify))
Specifics of 'Other' Storage Location (if selected) (TEXT)
Date of Material Receipt (DATE)
Materials Received (SELECTION options: Brick, Siding, Metal Panels, Flashing, Sealants, Fasteners)

Layout & Shop Drawings (STEP)
Shop Drawing Review Status (SELECTION options: Not Reviewed, Reviewed & Approved, Reviewed & Revised)
Shop Drawing Upload (UPLOAD)
Shop Drawing Accuracy Verification (SELECTION options: Accurate, Minor Discrepancies, Significant Discrepancies)
Discrepancy Notes (if applicable) (TEXT)
Offset Verification (if applicable) (NUMBER)
Building Line Offset Value (TEXT)
Vertical Alignment Verification (SELECTION options: Aligned as per Drawings, Minor Adjustment Required, Significant Adjustment Required)
Layout Approval Date (DATE)

System Installation (Specific to Cladding Type) (STEP)
Cladding Type Confirmed? (SELECTION options: Brick, Siding (Vinyl), Siding (Fiber Cement), Metal Panels (Aluminum), Metal Panels (Steel), Other (Specify))
Specific Installation Instructions/Notes for Cladding Type: (TEXT)
Number of Rows/Courses Installed (Brick): (NUMBER)
Number of Panels Installed: (NUMBER)
Panel/Brick Alignment Checks: (SELECTION options: Vertical Alignment, Horizontal Alignment, Spacing (Joint Width), Plumbness/Straightness)
Fastener Type Verified (if applicable): (SELECTION options: Screws, Nails, Adhesive, Other (Specify))
Photo Documentation of Installation (1-3 Photos) (UPLOAD)

Quality Control & Inspections (STEP)
Panel/Brick/Siding Alignment Tolerance (mm/inch) (NUMBER)
Joint Width Consistency (mm/inch) (NUMBER)
Panel/Brick/Siding Condition Upon Arrival (Visual Inspection) (SELECTION options: Excellent, Good, Acceptable (Minor imperfections noted), Unacceptable (Significant damage))
Identify Potential Issues (Check all that apply) (SELECTION options: Panel Bowing/Warping, Color Variation, Surface Defects, Incorrect Fastener Type, Incorrect Panel Placement, None Observed)
Detailed Observations/Corrective Actions Taken (TEXT)
Flashings Installed Correctly? (SELECTION options: Yes, No, NA (No Flashing Required))
Date of Inspection (DATE)
Time of Inspection (DATE)
Inspector Signature (SIGNATURE)
Supporting Photos (Optional) (UPLOAD)

Flashing & Waterproofing (STEP)
Flashing Material Verified? (SELECTION options: Yes, No, N/A)
Describe Flashing Installation Details (Material, Placement, Overlap) (TEXT)
Flashing Installed per Approved Details? (SELECTION options: Yes, No, N/A)
Flashing Overlap (Minimum) (NUMBER)
Note any deviations from specified flashing details. (TEXT)
Upload Photo of Flashing Installation (UPLOAD)
Membrane Waterproofing Installed (if applicable)? (SELECTION options: Yes, No, N/A)
Describe Waterproofing Application Method (TEXT)
Penetrations Properly Waterproofed? (SELECTION options: Yes, No, N/A)

Jointing & Sealing (STEP)
Joint Width (mm) (NUMBER)
Sealant Depth (mm) (NUMBER)
Sealant Type Verified? (SELECTION options: Yes - Matches Specification, No - Deviation Required, N/A)
Backer Rod Used? (SELECTION options: Yes, No, N/A)
Notes on Joint Condition/Application (TEXT)
Joint Surface Preparation Verified (Clean, Dry, Sound)? (SELECTION options: Yes, No, N/A)
Photo Documentation of Jointing/Sealing (UPLOAD)

Finishing & Cleanup (STEP)
Overall Appearance Assessment: Describe any visible imperfections (scratches, blemishes, etc.) (TEXT)
Surface Cleaning Required? (SELECTION options: Yes - Mild Cleaning, Yes - Moderate Cleaning, Yes - Heavy Cleaning, No - Satisfactory)
Details of Cleaning Procedure (if applicable) (TEXT)
Amount of Cleaning Solution Used (if applicable) (NUMBER)
Photographs of Finished Cladding System (UPLOAD)
Joint Sealer Condition? (SELECTION options: Satisfactory, Needs Adjustment, Needs Replacement)
Notes on joint sealant condition (if applicable) (TEXT)
Site Cleanup - Describe any remaining debris/waste. (TEXT)

Post-Installation & Documentation (STEP)
Final Inspection Date (DATE)
Inspector Name (TEXT)
Inspection Notes/Deficiencies (TEXT)
Warranty Period (Years) (NUMBER)
As-Built Drawings (UPLOAD)
Outstanding Items/Follow-up Required? (SELECTION options: Structural, Cosmetic, Waterproofing, None)
Contact Person for Follow-up (TEXT)
Completion Date (DATE)
Contractor Signature (SIGNATURE)