## 6a410ec48d045fc590b65e8d
Label	Description

Created by checklistguro.com

Start (START)	Start of the Workflow/Process
1. Fetch Asset Registry (ENTRY_GET)	Retrieve all existing equipment and machinery entries from the Asset Data Model to establish the implementation scope.
2. Create Implementation Project (ENTRY_CREATE)	Generate a new project entry in the Projects Data Model to track the CMMS rollout progress.
3. Site Survey Assignment (TASK_CREATE)	Create a task for the Field Engineer to physically audit equipment and verify data accuracy.
4. Update Asset Status (ENTRY_UPDATE)	Update the status of assets in the Data Model from 'Unverified' to 'Verified' following the site survey.
5. Calculate Total Asset Count (ENTRY_AGGREGATE)	Sum the total number of verified assets to determine the scale of the completed implementation phase.
6. Calculate Implementation Progress % (CALCULATION)	Execute a formula: (Total Verified Assets / Total Planned Assets) * 100 to determine completion percentage.
7. Configure Preventive Maintenance (PM) Schedules (TASK_CREATE)	Create a task for the Maintenance Planner to input PM frequencies and task checklists into the system.
8. Create PM Schedule Records (ENTRY_CREATE)	Generate individual maintenance schedule entries linked to the verified assets.
9. Fetch User Permissions (ENTRY_GET)	Retrieve the list of system users and their roles to assign appropriate access levels during setup.
10. User Training Session (TASK_CREATE)	Assign a task to the Implementation Lead to conduct training for the maintenance team.
11. Notify Stakeholders of Go-Live (EMAIL)	Send an email to the Operations Manager and Maintenance Manager announcing the system is ready for use.
12. Set Project Status to 'Live' (ENTRY_UPDATE)	Update the implementation project entry status to 'Completed/Live'.
13. Generate Final Implementation Report (REPORT_CREATE)	Create a summary report documenting the total assets migrated, PM schedules created, and training completion status.
14. Alert Site Manager (SMS)	Send an SMS to the Site Manager to notify them that the CMMS is officially operational.
End (END)	End of the Workflow/Process