## 6a410f0d8d045fc590b65f86
Label	Description

Created by checklistguro.com

Start (START)	Start of the Workflow/Process
1. Fetch System Requirements (ENTRY_GET)	Retrieve all User Requirements (URS) entries from the Requirements Data Model to initiate the validation scope.
2. Create Validation Plan Task (TASK_CREATE)	Assign a task to the QA Lead to draft the Validation Plan based on the identified system scope.
3. Generate Validation Plan Entry (ENTRY_CREATE)	Create a new entry in the Validation Plan data model containing the scope, strategy, and testing approach.
4. Risk Assessment Task (TASK_CREATE)	Assign a task to the Subject Matter Expert (SME) to perform a GAMP5-based risk assessment.
5. Create Risk Assessment Record (ENTRY_CREATE)	Create an entry in the Risk Management data model to document identified hazards and mitigation strategies.
6. Calculate Risk Priority Number (RPN) (CALCULATION)	Execute formula (Severity * Occurrence * Detectability) to determine the critical level of each risk.
7. Update Risk Mitigation Status (ENTRY_UPDATE)	Update the Risk Assessment entry to reflect that mitigation controls have been implemented.
8. Execute IQ/OQ/PQ Testing (TASK_CREATE)	Assign testing tasks to Validation Engineers to execute Installation, Operational, and Performance Qualifications.
9. Create Test Script Entry (ENTRY_CREATE)	Create a record in the Test Script data model for each protocol being executed.
10. Log Test Results (ENTRY_UPDATE)	Update the Test Script entry with pass/fail results and evidence links after execution.
11. Summarize Deviation Count (ENTRY_AGGREGATE)	Aggregate the number of 'Fail' statuses from all Test Script entries to determine total deviations.
12. Investigate Deviations Task (TASK_CREATE)	Create a task for the Quality Engineer if the Deviation Count is greater than zero.
13. Create Deviation Report (ENTRY_CREATE)	Create an entry in the Deviation Data Model for every failed test case identified.
14. Close Deviations (ENTRY_UPDATE)	Update the Deviation entries to 'Closed' once corrective actions are verified.
15. Generate Traceability Matrix Report (REPORT_CREATE)	Create a report linking Requirements $\rightarrow$ Risks $\rightarrow$ Test Scripts to ensure full coverage.
16. Final Summary Report Review (TASK_CREATE)	Assign a task to the Quality Manager to review the final Validation Summary Report (VSR).
17. Create Validation Summary Report (ENTRY_CREATE)	Create the final record in the Validation Summary data model summarizing the entire process outcome.
18. Notify Stakeholders of Approval (EMAIL)	Send an email to the Project Sponsor and IT Department once the VSR is approved and the system is released for production.
19. Update System Status to 'Validated' (ENTRY_UPDATE)	Update the Computer System entry in the Inventory Data Model to 'Validated' status.
End (END)	End of the Workflow/Process