## 6a390e415a1e7cf130c0ca1f
Label	Value	Notes

Created by ChecklistGuro (https://checklistguro.com)

Pre-Pour Planning & Preparation (STEP)
Scheduled Pour Date (DATE)
Scheduled Pour Start Time (DATE)
Estimated Concrete Volume (cubic yards) (NUMBER)
Weather Conditions Checked? (SELECTION options: Yes, No)
Weather Forecast Notes (temperature, precipitation) (TEXT)
Permits and Approvals Received? (SELECTION options: Yes, No)
Approved Pouring Plan/Sequence (UPLOAD)
Any Known Site Constraints or Concerns? (TEXT)

Formwork Inspection & Setup (STEP)
Formwork Depth Verification (inches) (NUMBER)
Formwork Bracing Condition (SELECTION options: Adequate, Insufficient, Needs Adjustment)
Formwork Alignment Condition (SELECTION options: Aligned, Slightly Misaligned, Significantly Misaligned)
Water Tightness of Formwork (SELECTION options: Watertight, Minor Leaks, Significant Leaks)
Notes on Formwork Condition (TEXT)
Formwork Photo Documentation (UPLOAD)
Distance between Formwork and Obstructions (inches) (NUMBER)

Reinforcement Placement & Verification (STEP)
Rebar Size Verification (Diameter) (NUMBER)
Rebar Spacing Verification (mm/inches) (NUMBER)
Rebar Grade Confirmation (e.g., 60, 75) (SELECTION options: Grade 60, Grade 65, Grade 75, Other (Specify))
Lap Splice Verification (SELECTION options: Lap Length Matches Plans, Tie Wire Present and Secure, Clearance around Splice Maintained)
Rebar Placement Photos (as evidence) (UPLOAD)
Notes on Rebar Installation (e.g., deviations from plans, adjustments made) (TEXT)
Mesh Size Verification (if applicable) (SELECTION options: Mesh size matches plan, Mesh size does not match plan, documented in notes)

Utilities & Embedded Items (STEP)
Utility Location Verification Complete? (SELECTION options: Yes, No)
Details of Utility Location Verification (if 'No' selected) (TEXT)
Number of Embedded Items (e.g., anchors, sleeves) (NUMBER)
Types of Embedded Items Present (SELECTION options: Anchor Bolts, Electrical Conduit, Plumbing Pipes, Sleeves, Other (Specify in Long Text))
Specify 'Other' Embedded Items (if 'Other' selected) (TEXT)
Photo of Embedded Items Placement (UPLOAD)
Utilities Protection Measures in Place? (SELECTION options: Yes, No)
Details of Utilities Protection Measures (if 'No' selected) (TEXT)

Concrete Delivery & Mixing (STEP)
Concrete Mix Design Strength (psi) (NUMBER)
Concrete Class (e.g., 3000psi, 4000psi) (SELECTION options: 3000 psi, 4000 psi, 5000 psi, Other (Specify in Long Text))
Specific Mix Design Details (Admixtures, etc.) (TEXT)
Scheduled Concrete Delivery Date (DATE)
Scheduled Concrete Delivery Time (DATE)
Estimated Concrete Volume (cubic yards) (NUMBER)
Concrete Supplier (SELECTION options: Supplier A, Supplier B, Supplier C, Other (Specify in Long Text))
Notes on Delivery Schedule or Requirements (TEXT)

Placement & Consolidation (STEP)
Concrete Pour Volume (cubic yards) (NUMBER)
Pour Start Time (DATE)
Pour Completion Time (DATE)
Concrete Slump (inches) (NUMBER)
Consolidation Method (SELECTION options: Manual, Vibrator (Internal), Vibrator (External), Other (Specify))
Consolidation Observations (e.g., vibrator coverage, air voids) (TEXT)
Concrete Placement Method (SELECTION options: Pump Truck, Chute, Bucket, Manual (Specify))
Notes on Placement (e.g., obstructions, unusual conditions) (TEXT)
Number of Concrete Bins Poured (NUMBER)

Finishing & Curing (STEP)
Finishing Method Employed? (SELECTION options: Screeding, Floating, Troweling, Broom Finish, Other (Specify))
Description of Finishing Process (details about tools, techniques, etc.) (TEXT)
Ambient Temperature (°C) (NUMBER)
Concrete Surface Temperature (°C) (NUMBER)
Curing Method Selected? (SELECTION options: Water Ponding, Wet Coverings, Curing Compound, Steam Curing, Other (Specify))
Details of Curing Implementation (frequency of wetting, type of compound used, etc.) (TEXT)
Start Date of Curing Process (DATE)
Thickness of Curing Compound Applied (if applicable) (NUMBER)

Post-Pour Inspection & Documentation (STEP)
Pour Completion Date (DATE)
Pour Completion Time (DATE)
Weather Conditions During Pour (TEXT)
Observations & Issues Encountered (TEXT)
Corrective Actions Taken (TEXT)
Concrete Temperature (at Placement) (NUMBER)
Air Temperature During Pour (NUMBER)
Concrete Finish Appearance (SELECTION options: Excellent, Acceptable, Needs Adjustment, Unacceptable)
Inspector Signature (SIGNATURE)