## Sheet1
Label | Value | Notes
Created by ChecklistGuro (https://checklistguro.com)
Initial Change Order Identification (STEP)
Date of Change Identification (DATE)
Change Order Reference Number (TEXT)
Origin of Change Request (SELECTION options: Owner Request, Architect/Engineer Instruction, Unforeseen Site Condition, Subcontractor Proposal, Regulatory/Permit Requirement)
Description of Deviation from Original Scope (TEXT)
Affected Project Area/Zone (LOCATION)
Supporting Photos or RFI Documentation (UPLOAD)
Initial Identifying Party Signature (SIGNATURE)
Impact Assessment & Cost Analysis (STEP)
Description of Scope Change (TEXT)
Detailed Cost Breakdown (TEXT)
Estimated Total Cost Impact (NUMBER)
Financial Impact Category (SELECTION options: Budget Increase, Budget Decrease, Budget Neutral)
Date of Impact Assessment (DATE)
Supporting Cost Estimates (UPLOAD)
Schedule & Timeline Evaluation (STEP)
Estimated New Completion Date (DATE)
Total Delay in Working Days (NUMBER)
Impact on Critical Path (SELECTION options: No Impact, Minor Impact (Non-Critical), Major Impact (Critical Path Affected))
Description of Schedule Delay Justification (TEXT)
Updated Project Schedule/Gantt Chart (UPLOAD)
Project Manager Schedule Verification (SIGNATURE)
Documentation & Supporting Evidence (STEP)
Date of Change Request (DATE)
Supporting Photos & Site Evidence (UPLOAD)
Revised Drawings or RFI Documents (UPLOAD)
Description of Deviation from Original Scope (TEXT)
Associated Documents Attached (SELECTION options: RFI (Request for Information), Subcontractor Quote, Updated Site Photos, Manufacturer Specifications, Material Delivery Tickets)
Originator Verification (SIGNATURE)
Stakeholder Review & Approvals (STEP)
Required Approval Parties (SELECTION options: Project Manager, Owner/Client, Architect/Engineer, Subcontractor, Quantity Surveyor)
Review Submission Date (DATE)
Approval Comments & Instructions (TEXT)
Authorized Approver Signature (SIGNATURE)
Signed Approval Document (UPLOAD)
Contract Amendment & Legal Compliance (STEP)
Amendment Execution Date (DATE)
Amendment Type (SELECTION options: Cost Increase, Cost Decrease, Schedule Extension Only, Scope Modification (No Cost/Time Change))
Legal Description of Contract Modification (TEXT)
Executed Legal Amendment Document (UPLOAD)
Authorized Project Representative Signature (SIGNATURE)
Compliance Checkpoints Completed (SELECTION options: Insurance Certificate Verified, Updated Bond Coverage Confirmed, Subcontractor Notice Provided, Legal Counsel Review Completed)
Post-Approval Implementation (STEP)
Implementation Start Date (DATE)
Updated Budget Allocation (TEXT)
Affected Project Workstreams (SELECTION options: Procurement, Subcontractors, Labor/Manpower, Equipment Rental, Material Delivery)
Updated Project Schedule/Gantt Chart (UPLOAD)
Project Manager Verification (SIGNATURE)
Final Closeout & Archiving (STEP)
Date of Final Archiving (DATE)
Archive Reference Number (TEXT)
Documents Uploaded to Project Directory (SELECTION options: Executed Change Order PDF, Updated Project Budget Sheet, Updated Project Schedule, Updated Site Photos)
Final Signed Approval Document (UPLOAD)
Project Manager Final Verification (SIGNATURE)
Archiving Notes & Discrepancy Remarks (TEXT)