## Sheet1
Label | Description
Created by checklistguro.com
Start (START) | Start of the Workflow/Process
1. Fetch Project Completion Data (ENTRY_GET) | Retrieve the final project entry and all associated financial and timeline data models.
2. Retrieve Project Team Members (ENTRY_GET) | Get all user entries linked to the project to identify stakeholders for the review.
3. Initialize Post-Project Review Record (ENTRY_CREATE) | Create a new entry in the 'Post-Project Reviews' data model to host the findings.
4. Assign Project Manager Review Task (TASK_CREATE) | Create a task for the PM to input qualitative feedback regarding project successes and failures.
5. Assign Site Supervisor Inspection Task (TASK_CREATE) | Create a task for the Site Supervisor to verify if all site safety protocols were closed out.
6. Update Review Status to 'In Progress' (ENTRY_UPDATE) | Update the newly created review entry status to reflect that the assessment has started.
7. Calculate Total Budget Variance (ENTRY_AGGREGATE) | Aggregate all cost entries from the project to compare actual spend vs. original budget.
8. Calculate Schedule Variance (ENTRY_AGGREGATE) | Aggregate planned vs. actual duration entries to calculate the total delay or early completion days.
9. Compute Profitability Margin (CALCULATION) | Execute formula: (Total Revenue - Total Actual Cost) / Total Revenue.
10. Conduct Lessons Learned Workshop (TASK_CREATE) | Create a task to schedule and host a meeting with all key stakeholders.
11. Log Identified Risks/Lessons (ENTRY_UPDATE) | Update the Review entry with specific data points captured during the workshop.
12. Create Risk Mitigation Entry (ENTRY_CREATE) | For every 'Lesson Learned' identified as a risk, create a new entry in the 'Risk Register' data model.
13. Finalize Review Documentation (ENTRY_UPDATE) | Update the Review entry status to 'Completed' once all tasks are closed.
14. Generate Post-Mortem Summary Report (REPORT_CREATE) | Generate a formal PDF report summarizing variances, budget performance, and key learnings.
15. Distribute Review Report to Stakeholders (EMAIL) | Send the generated summary report via email to the Project Sponsors and Executive Team.
16. Archive Project Data (ENTRY_UPDATE) | Update the original Project entry status to 'Archived' to signify the review cycle is closed.
End (END) | End of the Workflow/Process