## Sheet1
Label | Description
Created by checklistguro.com
Start (START) | Start of the Workflow/Process
1. Fetch Project Details (ENTRY_GET) | Retrieve project metadata such as site location, project manager, and total budget from the Project Data Model.
2. Retrieve Scheduled Milestones (ENTRY_GET) | Fetch all planned milestone dates from the Project Schedule Data Model to compare against actual progress.
3. Site Inspection Task (TASK_CREATE) | Create a task for the Site Supervisor to perform a physical walkthrough of the construction site.
4. Log Daily Progress Report (ENTRY_CREATE) | Create a new entry in the Daily Log Data Model containing observations, weather conditions, and labor counts.
5. Update Milestone Completion Status (ENTRY_UPDATE) | Update the 'Actual Completion Date' and 'Status' in the Milestone Data Model once a milestone is verified.
6. Get All Completed Tasks (ENTRY_GET) | Retrieve all completed tasks from the current work package to verify progress percentage.
7. Calculate Progress Percentage (ENTRY_AGGREGATE) | Aggregate the weightage of completed tasks versus total tasks to calculate the overall physical progress %.
8. Calculate Schedule Variance (CALCULATION) | Subtract the 'Planned Completion Date' from the 'Actual Completion Date' to identify delays (Days Variance).
9. Issue Non-Conformance Report (NCR) (TASK_CREATE) | Create a high-priority task for the Quality Control Engineer if a site inspection fails certain criteria.
10. Create NCR Entry (ENTRY_CREATE) | Generate a new entry in the Quality Issues Data Model to document the specific non-conformance found.
11. Notify Project Stakeholders of Delay (EMAIL) | Send an automated email to the Project Owner and Stakeholders if the Schedule Variance exceeds a specific threshold.
12. Retrieve Subcontractor Contact Info (ENTRY_GET) | Get contact details from the Vendor Data Model for the specific subcontractor responsible for the delayed work.
13. Urgent Alert to Site Manager (SMS) | Send an SMS alert to the Site Manager regarding critical safety or progress blockers identified during inspection.
14. Update Project Risk Register (ENTRY_UPDATE) | Update the 'Risk Level' or 'Impact Score' in the Risk Data Model based on the newly identified delay.
15. Generate Weekly Progress Report (REPORT_CREATE) | Generate a comprehensive PDF/Dashboard report summarizing progress, delays, and upcoming milestones for the week.
16. Remove Erroneous Daily Log (ENTRY_DELETE) | Delete a duplicate or incorrectly submitted Daily Log entry from the Data Model.
End (END) | End of the Workflow/Process