## Sheet1
Label | Description
Created by checklistguro.com
Start (START) | Start of the Workflow/Process
1. Retrieve Project Documentation (ENTRY_GET) | Fetch all completed inspection reports and technical manuals related to the specific construction project.
2. Update Project Status to 'Commissioning Phase' (ENTRY_UPDATE) | Change the status of the Construction Project entry to trigger the commissioning workflow.
3. Assign Site Engineer Inspection Task (TASK_CREATE) | Create a task for the assigned Site Engineer to perform the physical walkthrough and verify equipment installation.
4. Generate Commissioning Checklist (ENTRY_CREATE) | Create a new entry in the Checklist Data Model populated with standard commissioning requirements for the specific asset type.
5. Fetch Outstanding Snag List (ENTRY_GET) | Retrieve all unresolved 'Snag' or 'Defect' entries associated with the project.
6. Calculate Total Open Defects Count (ENTRY_AGGREGATE) | Aggregate the number of entries in the Snag List where status is 'Open' to determine if the project is ready for handover.
7. Calculate Completion Percentage (CALCULATION) | Calculate the ratio of completed commissioning tasks vs total tasks to determine the progress percentage.
8. Assign Quality Assurance Audit (TASK_CREATE) | Create a task for the QA Manager to verify that all checklists have been completed and signed off.
9. Update Snag List Status to 'Resolved' (ENTRY_UPDATE) | Update the status of all verified defects to 'Resolved' upon successful inspection.
10. Remove Obsolete Draft Documents (ENTRY_DELETE) | Delete temporary or superseded draft versions of manuals from the project documentation folder.
11. Notify Stakeholders of Commissioning Completion (EMAIL) | Send an email notification to the Project Owner and Client regarding the successful completion of the commissioning phase.
12. Generate Final Handover Report (REPORT_CREATE) | Compile all aggregated data, completed checklists, and final inspection results into a formal Handover Report PDF.
13. Create Handover Certificate (ENTRY_CREATE) | Create a new record in the Handover Certificate data model, linking it to the Project and the Final Report.
14. Alert Site Manager of Handover Approval (SMS) | Send an SMS alert to the Site Manager once the client has digitally signed the handover certificate.
15. Update Project Status to 'Handed Over' (ENTRY_UPDATE) | Finalize the project lifecycle by updating the Project entry status to 'Closed/Handed Over'.
End (END) | End of the Workflow/Process