## Sheet1
Label | Description
Created by checklistguro.com
Start (START) | Start of the Workflow/Process
1. Initialize Project Milestone Record (ENTRY_CREATE) | Create a new entry in the 'Project Milestones' data model to track the start of the construction phase.
2. Assign Site Survey Task (TASK_CREATE) | Create a task for the Site Engineer to perform the initial site inspection and measurements.
3. Update Milestone Status to 'In Progress' (ENTRY_UPDATE) | Update the status field of the Project Milestone entry to reflect that work has commenced.
4. Retrieve Budget Data (ENTRY_GET) | Get the allocated budget value from the 'Project Financials' data model.
5. Retrieve Actual Costs (ENTRY_GET) | Get all current expense entries related to the project to compare against the budget.
6. Calculate Total Project Spend (ENTRY_AGGREGATE) | Sum all 'Cost' properties from the 'Project Expenses' data model entries.
7. Calculate Budget Variance (CALCULATION) | Calculate the difference between the 'Retrieved Budget' and the 'Total Project Spend' (Budget - Total Spend).
8. Permit Verification Task (TASK_CREATE) | Create a task for the Compliance Officer to verify all local construction permits are valid.
9. Log Permit Approval (ENTRY_UPDATE) | Update the 'Permit Status' field in the Project Milestone entry to 'Verified'.
10. Notify Stakeholders of Milestone Completion (EMAIL) | Send an email to the Project Owner and Investors informing them that a specific milestone has been reached.
11. Alert Site Manager of Delay (SMS) | Send an SMS to the Site Manager if a critical milestone date has passed without completion.
12. Create Inspection Report Entry (ENTRY_CREATE) | Create a new entry in the 'Quality Inspection' data model following a site walkthrough.
13. Calculate Average Inspection Score (ENTRY_AGGREGATE) | Calculate the average value of 'Quality Score' from all inspection entries for the current milestone.
14. Issue Corrective Actions (TASK_CREATE) | If inspection scores are low, create tasks for the Subcontractors to fix identified issues.
15. Generate Milestone Progress Report (REPORT_CREATE) | Generate a visual report summarizing completed tasks, budget spend, and upcoming milestones.
16. Remove Draft Milestone Entries (ENTRY_DELETE) | Delete any duplicate or abandoned draft entries in the Milestone data model created during the planning phase.
End (END) | End of the Workflow/Process