## 6a410ef28d045fc590b65f29
Label	Description

Created by checklistguro.com

Start (START)	Start of the Workflow/Process
1. Initialize Inspection Record (ENTRY_CREATE)	Create a new entry in the 'Site Inspection' data model to initiate the QC process.
2. Fetch Project Details (ENTRY_GET)	Retrieve project metadata (Location, Project Manager, Deadline) from the 'Projects' data model.
3. Assign Site Walkthrough (TASK_CREATE)	Create a task for the Site Engineer to perform the physical inspection based on the inspection record.
4. Log Inspection Findings (ENTRY_UPDATE)	Update the 'Site Inspection' entry with notes, photos, and timestamped findings captured during the walkthrough.
5. Generate Non-Conformance Report (NCR) (ENTRY_CREATE)	If a failure is detected, create a new entry in the 'Non-Conformance' data model linked to the inspection.
6. Assign Remedial Action (TASK_CREATE)	Create a task for the Subcontractor to address the identified defect/non-conformance.
7. Check Previous NCRs (ENTRY_GET)	Retrieve all related entries from the 'Non-Conformance' model for the specific site area to check for recurring issues.
8. Calculate Defect Density (CALCULATION)	Calculate the ratio of failed inspection items to total inspected items using a formula.
9. Summarize Site Risk Score (ENTRY_AGGREGATE)	Aggregate the 'Severity' scores from all active NCR entries for the current project to determine risk level.
10. Close Non-Conformance (ENTRY_UPDATE)	Update the status of the 'Non-Conformance' entry to 'Resolved' once the remedial task is verified.
11. Notify Project Manager of Critical Failure (EMAIL)	Send an automated email to the PM when a 'High Severity' defect is logged.
12. Alert Site Supervisor of Safety Breach (SMS)	Send an SMS alert to the Supervisor if a safety-related non-conformance is identified.
13. Generate Weekly QC Summary (REPORT_CREATE)	Generate a PDF report aggregating all completed inspections and open NCRs for the weekly stakeholder meeting.
14. Remove Duplicate Inspection Drafts (ENTRY_DELETE)	Cleanup task to delete incorrectly duplicated or abandoned inspection drafts from the data model.
End (END)	End of the Workflow/Process