## 6a410ef08d045fc590b65f23
Label	Description

Created by checklistguro.com

Start (START)	Start of the Workflow/Process
1. Fetch Available Equipment (ENTRY_GET)	Retrieve all equipment entries from the Equipment Data Model that are currently marked as 'Available'.
2. Fetch Available Personnel (ENTRY_GET)	Retrieve all staff entries from the Resource Data Model with the 'Available' status.
3. Get Project Requirements (ENTRY_GET)	Get the specific resource requirements (hours, machinery, skillsets) from the active Construction Project entry.
4. Calculate Total Labor Cost (ENTRY_AGGREGATE)	Sum the hourly rates of all selected personnel assigned to the project.
5. Calculate Total Equipment Cost (ENTRY_AGGREGATE)	Sum the daily rental/usage costs of all selected machinery entries.
6. Calculate Total Resource Budget (CALCULATION)	Calculate the sum of Total Labor Cost and Total Equipment Cost to check against the project budget.
7. Calculate Resource Gap (CALCULATION)	Subtract total allocated hours from required project hours to identify under-allocation.
8. Assign Resource Manager (TASK_CREATE)	Create a task for the Resource Manager to review and approve the proposed allocation.
9. Update Site Schedule (TASK_CREATE)	Create a task for the Site Supervisor to adjust the construction timeline based on the allocated resources.
10. Create Allocation Record (ENTRY_CREATE)	Create a new entry in the 'Resource Allocation' data model to formalize the assignment.
11. Update Resource Status (ENTRY_UPDATE)	Update the status of the selected Personnel and Equipment entries from 'Available' to 'Allocated'.
12. Update Project Budget (ENTRY_UPDATE)	Update the 'Committed Costs' field in the Project entry with the new allocation totals.
13. Notify Project Manager (EMAIL)	Send an email to the Project Manager confirming that the resources have been successfully allocated.
14. Notify Personnel (EMAIL)	Send an email to the assigned staff members regarding their new project assignment and schedule.
15. Generate Allocation Summary Report (REPORT_CREATE)	Create a PDF report summarizing the allocated resources, costs, and duration for the project archives.
16. Remove Draft Allocation (ENTRY_DELETE)	Delete the temporary/draft allocation entry if the approval process is rejected.
End (END)	End of the Workflow/Process