## 6a410ef58d045fc590b65f35
Label	Description

Created by checklistguro.com

Start (START)	Start of the Workflow/Process
1. Retrieve Active Construction Projects (ENTRY_GET)	Fetch all current project entries to identify which sites are subject to upcoming risk assessments.
2. Identify High-Risk Hazards (ENTRY_GET)	Retrieve all identified hazards from the Hazard Log data model that have not yet been mitigated.
3. Create Risk Assessment Record (ENTRY_CREATE)	Generate a new Risk Assessment entry in the Risk Management data model when a new hazard is detected.
4. Calculate Risk Score (CALCULATION)	Calculate the Risk Priority Number (RPN) by multiplying Probability x Severity x Detectability.
5. Update Risk Severity Status (ENTRY_UPDATE)	Update the Risk entry with the newly calculated risk score and criticality level.
6. Sum Total Risk Exposure Value (ENTRY_AGGREGATE)	Aggregate the financial impact values of all 'High' priority risks to determine total potential loss.
7. Assign Mitigation Task to Site Manager (TASK_CREATE)	Create a task for the assigned Site Manager to develop a mitigation plan for high-score risks.
8. Create Safety Inspection Task (TASK_CREATE)	Generate a recurring inspection task for the Safety Officer to verify site compliance.
9. Notify Stakeholders of High Risk (EMAIL)	Send an automated email alert to Project Directors when a risk score exceeds the established threshold.
10. Urgent Site Alert (SMS)	Send an SMS notification to the On-site Supervisor if a critical/imminent danger risk is identified.
11. Log Mitigation Action (ENTRY_CREATE)	Create a new entry in the Mitigation Log to document the steps taken to reduce the risk.
12. Close Risk Entry (ENTRY_UPDATE)	Update the Risk entry status to 'Mitigated' or 'Closed' once all mitigation tasks are completed.
13. Generate Weekly Risk Compliance Report (REPORT_CREATE)	Generate a summary report of all active risks, mitigation progress, and outstanding tasks for the weekly safety meeting.
14. Remove False Positive Risks (ENTRY_DELETE)	Delete risk entries that were identified in error during the assessment process.
End (END)	End of the Workflow/Process