## 6a410e788d045fc590b65d8b
Label	Description

Created by checklistguro.com

Start (START)	Start of the Workflow/Process
1. Initial Site Inspection Task Assignment (TASK_CREATE)	Assigns the inspection task to the relevant site supervisor or inspector.
2. Retrieve Current Site Plan Data (ENTRY_GET)	Fetches necessary blueprints or site layout data model records for context.
3. Retrieve Safety Guideline Data (ENTRY_GET)	Gets the latest required safety standards and regulatory checklists from the data model.
4. Generate Deficiency Checklists (TASK_CREATE)	Creates specific inspection tasks based on the retrieved site plan and safety guidelines.
5. Record Inspection Findings (ENTRY_CREATE)	Allows inspectors to create new entries logging observations (deficiencies, completed checks) against a specific task.
6. Update Closure Status (ENTRY_UPDATE)	Updates the status of a previously logged deficiency (e.g., 'Open' to 'Closed').
7. Calculate Risk Score (CALCULATION)	Executes a formula to calculate a site risk score based on severity and number of findings.
8. Notify Project Manager of Critical Issues (EMAIL)	Sends an alert email to the Project Manager when a high-severity hazard is recorded.
9. Alert Site Foreman on Immediate Danger (SMS)	Sends an urgent SMS notification to the site foreman for immediate action required.
10. Generate Final Daily Inspection Report (REPORT_CREATE)	Compiles all inspection entries, calculations, and tasks into a formal, exportable report.
11. Summarize Completed Checklist Items (ENTRY_AGGREGATE)	Aggregates all 'Pass' entries to calculate the percentage of inspections completed.
12. Schedule Follow-up Inspection (TASK_CREATE)	Creates a future task reminder for necessary re-inspections of flagged areas.
End (END)	End of the Workflow/Process