## Sheet1
Label | Description
Created by checklistguro.com
Start (START) | Start of the Workflow/Process
1. Fetch Approved Vendors (ENTRY_GET) | Retrieve a list of all vendors from the Vendor Data Model who have passed recent compliance audits.
2. Check Inventory Levels (ENTRY_GET) | Query the Inventory Data Model to check current stock levels for required construction materials.
3. Calculate Total Order Value (CALCULATION) | Sum the unit prices multiplied by quantities for all items in the current procurement request.
4. Create Purchase Order (ENTRY_CREATE) | Generate a new entry in the Purchase Order Data Model once a requisition is approved.
5. Assign Procurement Officer (TASK_CREATE) | Create a task for the Procurement Manager to review and approve the newly created Purchase Order.
6. Update Vendor Status (ENTRY_UPDATE) | Update the 'Last Ordered Date' and 'Active' status in the Vendor Data Model after an order is placed.
7. Send PO to Vendor (EMAIL) | Send an automated email containing the Purchase Order details and attachments to the selected Vendor's email address.
8. Logistics Coordination (TASK_CREATE) | Create a task for the Logistics Team to arrange transport for the incoming materials.
9. Retrieve Delivery Schedule (ENTRY_GET) | Get existing delivery slots from the Logistics Data Model to avoid site congestion.
10. Create Delivery Receipt (ENTRY_CREATE) | Create an entry in the Delivery Data Model once the materials have arrived on-site.
11. Quality Inspection (TASK_CREATE) | Create a task for the Site Supervisor to perform a physical inspection of materials against the PO.
12. Calculate Variance (CALCULATION) | Compare the 'Delivered Quantity' against the 'Ordered Quantity' to identify discrepancies.
13. Update Inventory Stock (ENTRY_UPDATE) | Increase the quantity of materials in the Inventory Data Model based on the verified delivery.
14. Calculate Total Monthly Spend (ENTRY_AGGREGATE) | Aggregate all 'Order Value' entries from the Purchase Order Data Model for the current month.
15. Generate Monthly Procurement Report (REPORT_CREATE) | Create a summary report showing vendor performance, lead times, and total spend for management review.
16. Notify Site Manager of Arrival (SMS) | Send an SMS to the Site Manager when a high-priority delivery is confirmed for arrival.
17. Remove Expired Quotes (ENTRY_DELETE) | Delete quote entries from the Procurement Data Model that have exceeded their validity period.
End (END) | End of the Workflow/Process