## 6a410eef8d045fc590b65f1f
Label	Description

Created by checklistguro.com

Start (START)	Start of the Workflow/Process
1. Fetch Site Metadata (ENTRY_GET)	Retrieve project details, site location, and supervisor info from the Project Data Model.
2. Initialize Daily Report Entry (ENTRY_CREATE)	Create a new entry in the Daily Report Data Model for the current date and site.
3. Site Foreman: Morning Inspection (TASK_CREATE)	Assign a task to the Site Foreman to perform the initial safety and equipment walkthrough.
4. Site Foreman: Log Manpower & Equipment (TASK_CREATE)	Assign a task to log the number of workers and heavy machinery present on site today.
5. Update Work Progress (ENTRY_UPDATE)	Update the Daily Report entry with specific details regarding tasks completed vs. planned.
6. Log Incident/Accident (ENTRY_CREATE)	If an incident occurs, create a new entry in the Incident Report Data Model.
7. Safety Officer: Incident Review (TASK_CREATE)	Trigger a task for the Safety Officer if an Incident Entry was created.
8. Fetch Previous Day's Progress (ENTRY_GET)	Retrieve the previous day's completion percentage to compare with today's performance.
9. Calculate Labor Productivity (CALCULATION)	Calculate the ratio of completed work units vs. total man-hours logged today.
10. Aggregate Total Site Man-Hours (ENTRY_AGGREGATE)	Sum the total hours worked by all subcontractors listed in today's entries.
11. Finalize Daily Report (ENTRY_UPDATE)	Update the Daily Report entry status to 'Completed' and lock it for further editing.
12. Generate Daily Summary PDF (REPORT_CREATE)	Generate a formatted PDF report summarizing all activities, weather, and safety logs for the day.
13. Send Report to Project Manager (EMAIL)	Email the generated Daily Summary PDF to the Project Manager and Stakeholders.
14. Alert: High-Priority Delay (SMS)	Send an SMS alert to the Site Superintendent if the 'Delay' field in the entry is marked as 'Critical'.
15. Remove Duplicate Entries (ENTRY_DELETE)	Clean up any accidentally duplicated daily logs created by users.
End (END)	End of the Workflow/Process