## Sheet1
Label | Description
Created by checklistguro.com
Start (START) | Start of the Workflow/Process
1. Fetch Site Metadata (ENTRY_GET) | Retrieve project details, site location, and supervisor info from the Project Data Model.
2. Initialize Daily Report Entry (ENTRY_CREATE) | Create a new entry in the Daily Report Data Model for the current date and site.
3. Site Foreman: Morning Inspection (TASK_CREATE) | Assign a task to the Site Foreman to perform the initial safety and equipment walkthrough.
4. Site Foreman: Log Manpower & Equipment (TASK_CREATE) | Assign a task to log the number of workers and heavy machinery present on site today.
5. Update Work Progress (ENTRY_UPDATE) | Update the Daily Report entry with specific details regarding tasks completed vs. planned.
6. Log Incident/Accident (ENTRY_CREATE) | If an incident occurs, create a new entry in the Incident Report Data Model.
7. Safety Officer: Incident Review (TASK_CREATE) | Trigger a task for the Safety Officer if an Incident Entry was created.
8. Fetch Previous Day's Progress (ENTRY_GET) | Retrieve the previous day's completion percentage to compare with today's performance.
9. Calculate Labor Productivity (CALCULATION) | Calculate the ratio of completed work units vs. total man-hours logged today.
10. Aggregate Total Site Man-Hours (ENTRY_AGGREGATE) | Sum the total hours worked by all subcontractors listed in today's entries.
11. Finalize Daily Report (ENTRY_UPDATE) | Update the Daily Report entry status to 'Completed' and lock it for further editing.
12. Generate Daily Summary PDF (REPORT_CREATE) | Generate a formatted PDF report summarizing all activities, weather, and safety logs for the day.
13. Send Report to Project Manager (EMAIL) | Email the generated Daily Summary PDF to the Project Manager and Stakeholders.
14. Alert: High-Priority Delay (SMS) | Send an SMS alert to the Site Superintendent if the 'Delay' field in the entry is marked as 'Critical'.
15. Remove Duplicate Entries (ENTRY_DELETE) | Clean up any accidentally duplicated daily logs created by users.
End (END) | End of the Workflow/Process