## 6a4110138d045fc590b66303
Label	Description

Created by checklistguro.com

Start (START)	Start of the Workflow/Process
1. Fetch Event Requirements (ENTRY_GET)	Retrieve event details and quantities from the Event Master Data Model.
2. Initialize Production Project (ENTRY_CREATE)	Create a new production project entry linked to the specific event.
3. Retrieve Vendor Catalog (ENTRY_GET)	Get available swag items and their base costs from the Vendor Catalog model.
4. Design Artwork Task (TASK_CREATE)	Assign a task to the Graphic Designer to create branded assets for the selected items.
5. Update Artwork Status (ENTRY_UPDATE)	Update the 'Design Status' field in the Production Project once artwork is approved.
6. Get Vendor Quotes (TASK_CREATE)	Assign a task to the Procurement Officer to request pricing from suppliers.
7. Fetch Supplier Quotes (ENTRY_GET)	Retrieve all incoming quote entries related to the current production project.
8. Calculate Total Estimated Cost (CALCULATION)	Sum the unit costs and shipping fees from the retrieved quotes.
9. Create Purchase Order (ENTRY_CREATE)	Generate a new Purchase Order entry based on the selected vendor quote.
10. Production Monitoring Task (TASK_CREATE)	Assign a task to the Logistics Manager to track the manufacturing progress.
11. Update Production Progress (ENTRY_UPDATE)	Update the percentage completion field in the Production Project entry.
12. Aggregate Total Budget Spent (ENTRY_AGGREGATE)	Sum the total cost of all finalized Purchase Orders for the event.
13. Notify Stakeholders of Delivery Date (EMAIL)	Send an email to the Event Manager with the confirmed arrival date of the swag.
14. Quality Control Inspection (TASK_CREATE)	Assign a task to the Warehouse Team to inspect items upon arrival.
15. Finalize Inventory Receipt (ENTRY_UPDATE)	Update the inventory status to 'Received' in the Data Model.
16. Alert Logistics Driver (SMS)	Send an SMS to the driver notifying them that the swag is ready for pickup/delivery.
17. Production Post-Mortem Report (REPORT_CREATE)	Generate a report summarizing actual vs. budgeted costs and vendor performance.
18. Cleanup Draft Quotes (ENTRY_DELETE)	Delete rejected or expired quote entries from the system to maintain data hygiene.
End (END)	End of the Workflow/Process