## 6a410f6a8d045fc590b660c3
Label	Description

Created by checklistguro.com

Start (START)	Start of the Workflow/Process
1. Initialize Event Record (ENTRY_CREATE)	Create a new entry in the 'Events' data model with initial details like Event Name, Date, and Venue.
2. Assign Venue Scout (TASK_CREATE)	Create a task for the Logistics Manager to research and shortlist potential venues.
3. Update Venue Details (ENTRY_UPDATE)	Update the 'Events' entry with the selected venue information once confirmed.
4. Create Vendor Entry (ENTRY_CREATE)	Create a new entry in the 'Vendors' data model for catering, AV, or decor services.
5. Fetch Vendor Quotes (ENTRY_GET)	Retrieve all entries from the 'Quotes' data model associated with the current event.
6. Calculate Total Estimated Cost (ENTRY_AGGREGATE)	Aggregate the 'Price' property from all retrieved Vendor Quotes to find the total estimated budget.
7. Calculate Budget Variance (CALCULATION)	Calculate the difference between the 'Allocated Budget' and the 'Total Estimated Cost' (Budget - Total Cost).
8. Send Vendor Contracts (TASK_CREATE)	Create a task for the Legal/Admin user to distribute and collect signed contracts.
9. Notify Stakeholders (EMAIL)	Send an email to the Event Committee with the confirmed event date and venue location.
10. Retrieve Guest List (ENTRY_GET)	Get all entries from the 'Attendees' data model linked to this event.
11. Prepare Invitations (TASK_CREATE)	Create a task to design and finalize digital/physical invitations.
12. Send RSVP Reminder (SMS)	Send an SMS notification to guests who have not yet responded to the invitation.
13. Update Attendee Count (ENTRY_UPDATE)	Update the 'Confirmed Guest Count' field in the 'Events' entry based on RSVP responses.
14. Calculate Total Catering Demand (ENTRY_AGGREGATE)	Aggregate the 'Meal Preference' counts from the 'Attendees' list to provide a total for the caterer.
15. Finalize Event Itinerary (TASK_CREATE)	Create a task to create the minute-by-minute run sheet for the event day.
16. Generate Event Summary Report (REPORT_CREATE)	Create a final report summarizing the event budget, attendee numbers, and vendor performance.
17. Cleanup Draft Vendors (ENTRY_DELETE)	Delete entries from the 'Vendors' data model that were rejected during the selection process.
End (END)	End of the Workflow/Process