## 6a410f488d045fc590b6604e
Label	Description

Created by checklistguro.com

Start (START)	Start of the Workflow/Process
1. Retrieve Server Inventory (ENTRY_GET)	Fetch existing server and hardware records from the Asset Data Model to check availability.
2. Create Deployment Request (ENTRY_CREATE)	Initialize a new deployment record in the Infrastructure Request Data Model.
3. Hardware Provisioning Task (TASK_CREATE)	Assign a task to the Hardware Team to prepare physical servers and networking gear.
4. Update Asset Status (ENTRY_UPDATE)	Change the status of selected assets from 'In Stock' to 'In Deployment'.
5. Calculate Total Deployment Cost (CALCULATION)	Sum the cost of hardware, software licenses, and labor hours for the deployment budget.
6. Network Configuration Task (TASK_CREATE)	Assign a task to Network Engineers to configure VLANs, IP ranges, and firewall rules.
7. Fetch IP Address Pool (ENTRY_GET)	Retrieve available IP addresses from the Network Configuration Data Model.
8. Create Network Configuration Entry (ENTRY_CREATE)	Create a new record detailing the specific IP and VLAN assignments for the new infrastructure.
9. OS Installation Task (TASK_CREATE)	Assign a task to System Administrators to install and patch the Operating Systems.
10. Log OS Installation Details (ENTRY_UPDATE)	Update the deployment record with OS version, build number, and installation timestamp.
11. Aggregate Resource Usage (ENTRY_AGGREGATE)	Calculate the total CPU and RAM consumption of the newly deployed nodes.
12. Security Compliance Audit (TASK_CREATE)	Assign a task to the Security Team to run vulnerability scans on the new infrastructure.
13. Retrieve Security Baseline (ENTRY_GET)	Fetch the standard security configuration requirements from the Compliance Data Model.
14. Update Security Compliance Status (ENTRY_UPDATE)	Mark the infrastructure as 'Compliant' or 'Non-Compliant' based on audit results.
15. Notify Stakeholders (EMAIL)	Send an email to Project Managers and Department Heads announcing the deployment completion.
16. Final Documentation Task (TASK_CREATE)	Assign a task to the Documentation Specialist to update the Network Topology Diagrams.
17. Create Asset End-of-Life Record (ENTRY_CREATE)	Create an entry in the Lifecycle Data Model to track the decommission date for the hardware.
18. Generate Deployment Summary Report (REPORT_CREATE)	Generate a final report containing the deployment timeline, costs, and hardware specifications.
19. Remove Temporary Deployment Logs (ENTRY_DELETE)	Delete temporary staging logs and installation scratchpad entries from the system.
20. Urgent Alert: Deployment Failure (SMS)	Send an SMS to the On-Call Engineer if any critical step in the deployment fails.
End (END)	End of the Workflow/Process