## 6a410ec78d045fc590b65e97
Label	Description

Created by checklistguro.com

Start (START)	Start of the Workflow/Process
1. Retrieve Pending Maintenance Requests (ENTRY_GET)	Fetch all entries from the Maintenance Requests data model where status is 'New' or 'Unassigned'.
2. Fetch Asset Information (ENTRY_GET)	Retrieve details from the Assets data model (e.g., age, warranty status) associated with the maintenance request.
3. Calculate Estimated Repair Cost (CALCULATION)	Calculate total cost by summing parts_cost and labor_cost retrieved from the request.
4. Create Maintenance Work Order (ENTRY_CREATE)	Create a new entry in the Work Orders data model based on the maintenance request details.
5. Assign Technician Task (TASK_CREATE)	Create a task for the Maintenance Manager to review and assign a technician to the newly created Work Order.
6. Update Request Status (ENTRY_UPDATE)	Update the original Maintenance Request entry status to 'In Progress'.
7. Get Parts Inventory Prices (ENTRY_GET)	Retrieve unit prices for the required parts from the Inventory data model.
8. Calculate Total Budget Impact (CALCULATION)	Calculate the sum of parts and labor against the remaining annual maintenance budget.
9. Aggregate Monthly Maintenance Spend (ENTRY_AGGREGATE)	Calculate the SUM of all completed maintenance costs for the current month to track budget consumption.
10. Update Asset Maintenance Log (ENTRY_UPDATE)	Update the 'Last Maintenance Date' field in the Assets data model for the specific asset being repaired.
11. Technician Completion Task (TASK_CREATE)	Create a task for the assigned technician to complete the repair and log actual costs.
12. Retrieve Actual Costs (ENTRY_GET)	Get the final parts and labor cost entries from the completed Work Order.
13. Finalize Work Order (ENTRY_UPDATE)	Update the Work Order status to 'Closed' and set the final cost field.
14. Calculate Total Cost Variance (ENTRY_AGGREGATE)	Calculate the difference between the Estimated Repair Cost and the Final Actual Cost.
15. Notify Finance Department (EMAIL)	Send an email to the Finance team with the summary of the completed maintenance cost for budget reconciliation.
16. Generate Monthly Maintenance Cost Report (REPORT_CREATE)	Create a structured report aggregating all maintenance expenditures, assets serviced, and budget variances for the month.
End (END)	End of the Workflow/Process