## 6a410e518d045fc590b65d05
Label	Description

Created by checklistguro.com

Start (START)	Start of the Workflow/Process
1. Retrieve Current Bill of Materials (BOM) (ENTRY_GET)	Fetch the existing BOM for the affected product.
2. Retrieve Affected Work Instructions (ENTRY_GET)	Identify work instructions impacted by the proposed change.
3. Notify Engineering Team (TASK_CREATE)	Create a task for the engineering team to review the change request.
4. Create Change Request Entry (ENTRY_CREATE)	Document details of proposed change including justification and impact assessment.
5. Assign Reviewer (Quality) (TASK_CREATE)	Create a task to assign a quality reviewer to assess the change.
6. Send Change Request Notification (EMAIL)	Email notification to relevant stakeholders regarding the change request.
7. Update Change Request Status (ENTRY_UPDATE)	Update the status of the change request (e.g., 'Under Review', 'Approved', 'Rejected').
8. Schedule Impact Analysis (TASK_CREATE)	Create a task to perform a detailed impact analysis of the proposed change.
9. Calculate Change Cost (CALCULATION)	Calculate the estimated cost of implementing the change (labor, materials, equipment).
10. Create New Revision of BOM (ENTRY_CREATE)	Create a new version of the Bill of Materials reflecting the changes.
11. Notify Production Planning (TASK_CREATE)	Create a task to inform production planning about the upcoming change.
12. Update Product Data Model (ENTRY_UPDATE)	Update relevant fields in the product data model with the new information.
13. Generate Change Impact Report (REPORT_CREATE)	Create a report summarizing the impact of the change, including cost, timeline, and potential risks.
14. Retrieve Previous Revision of Document (ENTRY_GET)	Get the previous version of the affected document for comparison.
15. Train Production Staff (TASK_CREATE)	Create a task to train production staff on the new processes/BOM.
End (END)	End of the Workflow/Process