## 6a410e558d045fc590b65d13
Label	Description

Created by checklistguro.com

Start (START)	Start of the Workflow/Process
1. Retrieve Current ECO Data (ENTRY_GET)	Fetch existing ECO data from the ECO data model.
2. Notify Engineering Lead (TASK_CREATE)	Create a task for the Engineering Lead to review the ECO request.
3. Send Initial ECO Notification (EMAIL)	Email notification to relevant stakeholders regarding the submitted ECO.
4. Create ECO Request Entry (ENTRY_CREATE)	Create a new entry in the ECO Request data model.
5. Assign Impact Assessment (TASK_CREATE)	Create a task to assess the impact of the proposed change.
6. Calculate Estimated Cost (CALCULATION)	Calculate the estimated cost of the change based on material and labor costs.
7. Update ECO Status (ENTRY_UPDATE)	Update the ECO status field in the ECO data model.
8. Retrieve Affected BOMs (ENTRY_GET)	Fetch BOMs potentially impacted by the ECO.
9. Review and Approve BOM Changes (TASK_CREATE)	Create a task for BOM engineers to review and approve necessary changes.
10. Send Approval Notification (EMAIL)	Email notification upon ECO approval.
11. Create Revision History Entry (ENTRY_CREATE)	Create a new entry in the ECO Revision History data model to track changes.
12. Generate ECO Summary Report (REPORT_CREATE)	Create a report summarizing the ECO details, impact assessment, and approval status.
13. Notify Production Planning (TASK_CREATE)	Create a task for Production Planning to prepare for implementation.
14. Update Implementation Status (ENTRY_UPDATE)	Update the implementation status field in the ECO data model.
15. Retrieve related Work Orders (ENTRY_GET)	Fetch relevant work orders impacted by the ECO.
End (END)	End of the Workflow/Process