## 6a410e588d045fc590b65d1b
Label	Description

Created by checklistguro.com

Start (START)	Start of the Workflow/Process
1. Retrieve Initial Design Specifications (ENTRY_GET)	Fetch initial design specifications from the product design data model.
2. Assign Design Review Task (TASK_CREATE)	Create a task for the engineering team to review the design specifications.
3. Create Preliminary Bill of Materials (BOM) (ENTRY_CREATE)	Create a preliminary BOM based on the design specifications.
4. Create Process Flow Diagram (ENTRY_CREATE)	Create a preliminary process flow diagram outlining the manufacturing steps.
5. Factory Feasibility Assessment Task (TASK_CREATE)	Assign a task to assess manufacturing feasibility at the factory.
6. Send Initial NPI Kickoff Email (EMAIL)	Send an email to relevant stakeholders announcing the NPI process initiation.
7. Create Prototype Production Plan (ENTRY_CREATE)	Define the prototype production plan, including quantity and timeline.
8. Prototype Build Task Assignment (TASK_CREATE)	Assign the prototype build task to the manufacturing team.
9. Update BOM with Prototype Feedback (ENTRY_UPDATE)	Update the BOM based on feedback from the prototype build.
10. Retrieve Prototype Test Results (ENTRY_GET)	Fetch the test results from the prototype testing phase.
11. Generate Prototype Test Report (REPORT_CREATE)	Create a report summarizing the prototype test results.
12. Process Validation Task Assignment (TASK_CREATE)	Assign the task of validating the manufacturing process.
13. Update Manufacturing Instructions (ENTRY_UPDATE)	Update manufacturing instructions with process validation findings.
14. Send NPI Launch Notification (SMS)	Send an SMS notification to key personnel regarding the product launch.
15. Create Production Ramp-Up Plan (ENTRY_CREATE)	Define the plan for scaling up production volume.
End (END)	End of the Workflow/Process