## 6a410f308d045fc590b65ffd
Label	Description

Created by checklistguro.com

Start (START)	Start of the Workflow/Process
1. Initialize Outage Event (ENTRY_CREATE)	Create a new Outage Event entry in the Outage Data Model to define start/end dates and scope.
2. Safety Permit Review (TASK_CREATE)	Assign a task to the Safety Officer to review and approve the high-risk work permits required for the outage.
3. Retrieve Spare Parts Inventory (ENTRY_GET)	Fetch all critical spare parts entries from the Inventory Data Model to verify availability for the outage scope.
4. Update Resource Allocation (ENTRY_UPDATE)	Update the Outage Event entry with the confirmed list of contractors and technicians assigned to the period.
5. Equipment Inspection Execution (TASK_CREATE)	Create tasks for technicians to perform physical inspections on turbines, boilers, and auxiliary systems.
6. Log Inspection Findings (ENTRY_CREATE)	Create new entries in the Inspection Findings Data Model for every defect or anomaly discovered during inspection.
7. Calculate Estimated Repair Cost (CALCULATION)	Calculate the total estimated cost by summing labor hours and parts cost identified in the inspection findings.
8. Total Findings Summary (ENTRY_AGGREGATE)	Aggregate all inspection findings to count the total number of critical vs. non-critical defects found.
9. Critical Repair Execution (TASK_CREATE)	Create high-priority tasks for the engineering team to address all 'Critical' flagged findings.
10. Budget Overrun Alert (EMAIL)	Send an automated email to the Plant Manager if the calculated repair cost exceeds the predefined outage budget.
11. Update Outage Schedule (ENTRY_UPDATE)	Update the Outage Event entry with the revised completion date based on the repair progress.
12. Final Testing & Commissioning (TASK_CREATE)	Assign tasks to the operations team to run sequence tests and pressure tests before synchronization.
13. Generate Outage Post-Mortem Report (REPORT_CREATE)	Generate a comprehensive report summarizing all tasks completed, costs incurred, and findings recorded.
14. Plant Ready for Synchronization Alert (SMS)	Send an SMS notification to the Grid Dispatcher indicating that the plant is ready to reconnect to the grid.
15. Close Outage Event (ENTRY_UPDATE)	Update the Outage Event status to 'Completed' and archive the event data.
End (END)	End of the Workflow/Process