## Sheet1
Label | Description
Created by checklistguro.com
Start (START) | Start of the Workflow/Process
1. Initialize Lead/Project Entry (ENTRY_CREATE) | Create a new entry in the 'Projects' data model to initiate the estimation process.
2. Fetch Project Specifications (ENTRY_GET) | Retrieve blueprint and requirement data from the Project entry to populate estimation parameters.
3. Site Visit Assignment (TASK_CREATE) | Create a task for the Field Engineer to perform a physical site inspection.
4. Create Site Inspection Report (ENTRY_CREATE) | Generate a new entry in the 'Site Inspection' data model linked to the Project.
5. Quantity Takeoff (TASK_CREATE) | Assign a task to the Estimator to measure and count materials from the digital blueprints.
6. Create Material Takeoff Entry (ENTRY_CREATE) | Create a line-item entry in the 'Material Takeoff' data model for each identified material.
7. Fetch Material Unit Costs (ENTRY_GET) | Retrieve current pricing from the 'Vendor Price List' data model.
8. Calculate Material Subtotal (CALCULATION) | Multiply Quantity (from Takeoff) by Unit Cost (from Price List) to get the subtotal per item.
9. Sum Total Material Costs (ENTRY_AGGREGATE) | Aggregate all material subtotal entries to calculate the total direct material cost.
10. Calculate Labor & Overhead (CALCULATION) | Apply labor multiplier and overhead percentage to the total material cost.
11. Calculate Final Bid Price (CALCULATION) | Sum Material Costs, Labor, and Overhead, then add the desired profit margin.
12. Internal Bid Review (TASK_CREATE) | Create a task for the Pre-Construction Manager to review the calculated estimate for accuracy.
13. Update Project Status to 'Review' (ENTRY_UPDATE) | Update the Project entry status field to indicate the estimate is ready for review.
14. Generate Bid Proposal (ENTRY_CREATE) | Create a formal 'Proposal' entry containing the final numbers and terms.
15. Send Proposal to Client (EMAIL) | Send the finalized proposal and documentation to the client's email address.
16. Follow-up Task (TASK_CREATE) | Create a follow-up task for the Sales Rep to contact the client 3 days after proposal submission.
17. Update Project to 'Bid Submitted' (ENTRY_UPDATE) | Update the Project entry to reflect that the bid is officially out for tender.
18. Record Bid Outcome (ENTRY_UPDATE) | Update the Project entry with 'Won' or 'Lost' status based on client feedback.
19. Monthly Bidding Performance Report (REPORT_CREATE) | Generate a report summarizing Win/Loss ratios and total bid volume for the month.
End (END) | End of the Workflow/Process