## 6a410f4c8d045fc590b6605d
Label	Description

Created by checklistguro.com

Start (START)	Start of the Workflow/Process
1. Fetch Unrefined Backlog Items (ENTRY_GET)	Retrieve all backlog entries from the Product Backlog data model that have a status of 'New' or 'Unrefined'.
2. Mark Items as 'In Grooming' (ENTRY_UPDATE)	Update the status of the selected backlog entries to 'In Grooming' to prevent duplicate processing.
3. Schedule Grooming Session (TASK_CREATE)	Create a task for the Product Owner to organize the upcoming grooming meeting.
4. Get Refinement Criteria (ENTRY_GET)	Retrieve the Definition of Ready (DoR) standards from the Process Standards data model.
5. Assign Story Splitting Task (TASK_CREATE)	Create a task for the Development Team to break down large Epics into manageable User Stories.
6. Update Story Points/Estimation (ENTRY_UPDATE)	Update the estimation field in the Backlog entries based on the team's consensus during the session.
7. Calculate Total Story Point Volatility (CALCULATION)	Calculate the sum of all story points assigned to the current grooming batch to assess workload.
8. Calculate Total Backlog Size (ENTRY_AGGREGATE)	Aggregate the sum of all story points across the entire backlog to visualize total technical debt/scope.
9. Set Priority Level (ENTRY_UPDATE)	Update the priority field of the backlog entries based on the outcome of the grooming discussion.
10. Create Sprint Ready Items (ENTRY_CREATE)	Create new entries in the 'Sprint Ready' data model for all items that now meet the Definition of Ready.
11. Notify Stakeholders (TASK_CREATE)	Create a task for the Product Manager to inform stakeholders of the updated roadmap/priorities.
12. Send Grooming Summary (EMAIL)	Send an email to the Development Team and Product Owner containing the list of newly refined items.
13. Generate Backlog Health Report (REPORT_CREATE)	Create a report showing the ratio of 'Ready' vs 'Unrefined' items in the backlog.
14. Remove Duplicate Items (ENTRY_DELETE)	Delete any backlog entries identified as duplicates during the grooming session.
End (END)	End of the Workflow/Process