## Sheet1
Label | Description
Created by checklistguro.com
Start (START) | Start of the Workflow/Process
1. Fetch Unrefined Backlog Items (ENTRY_GET) | Retrieve all backlog entries from the Product Backlog data model that have a status of 'New' or 'Unrefined'.
2. Mark Items as 'In Grooming' (ENTRY_UPDATE) | Update the status of the selected backlog entries to 'In Grooming' to prevent duplicate processing.
3. Schedule Grooming Session (TASK_CREATE) | Create a task for the Product Owner to organize the upcoming grooming meeting.
4. Get Refinement Criteria (ENTRY_GET) | Retrieve the Definition of Ready (DoR) standards from the Process Standards data model.
5. Assign Story Splitting Task (TASK_CREATE) | Create a task for the Development Team to break down large Epics into manageable User Stories.
6. Update Story Points/Estimation (ENTRY_UPDATE) | Update the estimation field in the Backlog entries based on the team's consensus during the session.
7. Calculate Total Story Point Volatility (CALCULATION) | Calculate the sum of all story points assigned to the current grooming batch to assess workload.
8. Calculate Total Backlog Size (ENTRY_AGGREGATE) | Aggregate the sum of all story points across the entire backlog to visualize total technical debt/scope.
9. Set Priority Level (ENTRY_UPDATE) | Update the priority field of the backlog entries based on the outcome of the grooming discussion.
10. Create Sprint Ready Items (ENTRY_CREATE) | Create new entries in the 'Sprint Ready' data model for all items that now meet the Definition of Ready.
11. Notify Stakeholders (TASK_CREATE) | Create a task for the Product Manager to inform stakeholders of the updated roadmap/priorities.
12. Send Grooming Summary (EMAIL) | Send an email to the Development Team and Product Owner containing the list of newly refined items.
13. Generate Backlog Health Report (REPORT_CREATE) | Create a report showing the ratio of 'Ready' vs 'Unrefined' items in the backlog.
14. Remove Duplicate Items (ENTRY_DELETE) | Delete any backlog entries identified as duplicates during the grooming session.
End (END) | End of the Workflow/Process