## 6a410f718d045fc590b660da
Label	Description

Created by checklistguro.com

Start (START)	Start of the Workflow/Process
1. Fetch Unrefined Backlog Items (ENTRY_GET)	Retrieve all entries from the 'Product Backlog' data model where status is 'New' or 'Unrefined'.
2. Fetch Product Roadmap (ENTRY_GET)	Retrieve upcoming milestones from the 'Roadmap' data model to align grooming with high-level goals.
3. Retrieve Team Capacity (ENTRY_GET)	Get current developer availability and sprint velocity from the 'Resource' data model.
4. Calculate Feature Priority Score (CALCULATION)	Apply a formula (e.g., Impact * Confidence / Effort) to determine the relative priority of the feature.
5. Assign Refinement Task (TASK_CREATE)	Create a task for the Product Owner to review and add acceptance criteria to the selected backlog items.
6. Update Feature Status to 'Refining' (ENTRY_UPDATE)	Update the status of the selected backlog entries to 'In Refinement' to prevent duplicate work.
7. Assign Technical Spike Task (TASK_CREATE)	Create a task for the Engineering Lead if a feature requires technical investigation/research.
8. Fetch Technical Spike Results (ENTRY_GET)	Retrieve the completed notes and complexity estimates from the 'Spike Results' data model.
9. Update Feature Story Points (ENTRY_UPDATE)	Update the 'Effort/Story Points' field in the Backlog data model based on the outcome of the grooming session.
10. Calculate Total Backlog Effort (ENTRY_AGGREGATE)	Sum the 'Story Points' of all items currently in the 'Ready for Sprint' status to check against capacity.
11. Create Sprint Ready Item (ENTRY_CREATE)	Create a new entry in the 'Sprint Ready' data model for features that have passed all grooming criteria.
12. Finalize Feature Acceptance Criteria (ENTRY_UPDATE)	Update the 'Definition of Ready' checkbox and 'Acceptance Criteria' text field in the backlog entry.
13. Notify Stakeholders of Refined Features (EMAIL)	Send an email to the Stakeholder list with a summary of the newly refined features and their priorities.
14. Generate Grooming Summary Report (REPORT_CREATE)	Generate a report showing the change in backlog health, total points refined, and upcoming high-priority items.
15. Remove Deprecated Features (ENTRY_DELETE)	Delete or move to 'Archive' any backlog entries that were identified as redundant during the grooming process.
End (END)	End of the Workflow/Process