## 6a410f478d045fc590b6604c
Label	Description

Created by checklistguro.com

Start (START)	Start of the Workflow/Process
1. Initialize Product Launch Record (ENTRY_CREATE)	Create a new entry in the 'Product Launches' data model to initiate the lifecycle.
2. Define Product Requirements (TASK_CREATE)	Assign a task to the Product Manager to document core features and specifications.
3. Create Market Research Task List (ENTRY_CREATE)	Create a linked entry in the 'Research' data model containing specific competitive analysis items.
4. Retrieve Budget Allocation (ENTRY_GET)	Fetch the total allocated budget from the 'Marketing Budgets' data model.
5. Check Resource Availability (ENTRY_GET)	Get entries from the 'Team Members' data model to identify available designers and developers.
6. Calculate Remaining Launch Budget (CALCULATION)	Subtract total estimated costs from the retrieved Budget Allocation.
7. Design Brand Assets (TASK_CREATE)	Create a task for the Creative Team to develop logos, banners, and social media assets.
8. Update Product Milestone Status (ENTRY_UPDATE)	Update the 'Launch Roadmap' entry to reflect that the 'Design Phase' is complete.
9. Sum Total Development Costs (ENTRY_AGGREGATE)	Aggregate the 'Cost' property from all 'Development Tasks' associated with this launch.
10. Update Launch Timeline (ENTRY_UPDATE)	Update the 'Estimated Launch Date' in the Product Launch record based on new development estimates.
11. Execute QA Testing (TASK_CREATE)	Create a task for the QA Team to run end-to-end testing on the product.
12. Fetch Bug Reports (ENTRY_GET)	Retrieve all 'Bug' entries from the 'Issue Tracker' data model associated with this product version.
13. Calculate Bug Severity Average (ENTRY_AGGREGATE)	Calculate the average severity score of all open bugs to determine launch readiness.
14. Flag Critical Launch Blockers (ENTRY_UPDATE)	Update the Product Launch entry to 'At Risk' status if critical bugs are found.
15. Notify Stakeholders of Launch Date (EMAIL)	Send an email to the Executive Team with the finalized launch date and budget summary.
16. Prepare Marketing Campaign (TASK_CREATE)	Create a task for the Marketing Lead to finalize ad copy and channel scheduling.
17. Generate Launch Checklist (ENTRY_CREATE)	Create a new entry in the 'Checklists' data model populated with final pre-launch steps.
18. Alert Operations Team (SMS)	Send an SMS to the Operations Lead to ensure server capacity is ready for the traffic spike.
19. Generate Launch Readiness Report (REPORT_CREATE)	Create a comprehensive report summarizing budget, bugs, and task completion status for final sign-off.
20. Set Status to 'Live' (ENTRY_UPDATE)	Update the Product Launch record status to 'Launched'.
21. Archive Temporary Research Notes (ENTRY_DELETE)	Delete temporary, non-permanent research entries to keep the data model clean post-launch.
End (END)	End of the Workflow/Process