## 6a410ef48d045fc590b65f2f
Label	Description

Created by checklistguro.com

Start (START)	Start of the Workflow/Process
1. Retrieve Project Master Data (ENTRY_GET)	Fetch project details (Project Name, Client, End Date) from the Project Data Model to populate the closeout record.
2. Initialize Closeout Record (ENTRY_CREATE)	Create a new entry in the Project Closeout Data Model to track the progress of the decommissioning process.
3. Fetch Open Punch List Items (ENTRY_GET)	Retrieve all active tasks and entries from the Punch List Data Model that are not yet marked as 'Resolved'.
4. Assign Final Site Inspection (TASK_CREATE)	Create a task for the Site Manager to conduct a final walkthrough and verify all physical works are complete.
5. Update Punch List Status (ENTRY_UPDATE)	Update the status of specific punch list entries to 'Verified' once the inspection task is completed.
6. Calculate Total Open Punch List Items (ENTRY_AGGREGATE)	Count the total number of remaining unresolved entries in the Punch List Data Model.
7. Calculate Completion Percentage (CALCULATION)	Execute formula: (Resolved Items / Total Items) * 100 to determine the project's closure readiness.
8. Assign Punch List Remediation (TASK_CREATE)	Create tasks for subcontractors/technicians to address the specific items identified in the inspection.
9. Get Subcontractor Contact Info (ENTRY_GET)	Retrieve contact details from the Vendor Data Model for all parties involved in the punch list items.
10. Notify Stakeholders of Inspection (EMAIL)	Send an automated email to the Project Manager and Client notifying them that the final inspection is scheduled.
11. Update Project Status to 'Closing' (ENTRY_UPDATE)	Change the status field in the Project Data Model from 'Active' to 'In Closeout'.
12. Document Archiving (TASK_CREATE)	Create a task for the Project Admin to ensure all manuals, warranties, and as-built drawings are uploaded.
13. Create Final Project Report Entry (ENTRY_CREATE)	Create a summary entry in the Archive Data Model containing the final project metrics.
14. Generate Closeout Summary Report (REPORT_CREATE)	Generate a PDF report containing the final punch list resolution stats, total costs, and completion dates.
15. Send Final Handover Package (EMAIL)	Send an email to the Client containing the link to the Final Project Report and the completed Punch List.
16. Set Project Status to 'Closed' (ENTRY_UPDATE)	Update the Project Data Model status to 'Closed' to trigger the end of the project lifecycle.
17. Cleanup Temporary Work Orders (ENTRY_DELETE)	Delete temporary/adhoc work order entries that were only created for the duration of the punch list phase.
End (END)	End of the Workflow/Process