## Sheet1
Label | Description
Created by checklistguro.com
Start (START) | Start of the Workflow/Process
1. Retrieve Project Master Data (ENTRY_GET) | Fetch project details (Project Name, Client, End Date) from the Project Data Model to populate the closeout record.
2. Initialize Closeout Record (ENTRY_CREATE) | Create a new entry in the Project Closeout Data Model to track the progress of the decommissioning process.
3. Fetch Open Punch List Items (ENTRY_GET) | Retrieve all active tasks and entries from the Punch List Data Model that are not yet marked as 'Resolved'.
4. Assign Final Site Inspection (TASK_CREATE) | Create a task for the Site Manager to conduct a final walkthrough and verify all physical works are complete.
5. Update Punch List Status (ENTRY_UPDATE) | Update the status of specific punch list entries to 'Verified' once the inspection task is completed.
6. Calculate Total Open Punch List Items (ENTRY_AGGREGATE) | Count the total number of remaining unresolved entries in the Punch List Data Model.
7. Calculate Completion Percentage (CALCULATION) | Execute formula: (Resolved Items / Total Items) * 100 to determine the project's closure readiness.
8. Assign Punch List Remediation (TASK_CREATE) | Create tasks for subcontractors/technicians to address the specific items identified in the inspection.
9. Get Subcontractor Contact Info (ENTRY_GET) | Retrieve contact details from the Vendor Data Model for all parties involved in the punch list items.
10. Notify Stakeholders of Inspection (EMAIL) | Send an automated email to the Project Manager and Client notifying them that the final inspection is scheduled.
11. Update Project Status to 'Closing' (ENTRY_UPDATE) | Change the status field in the Project Data Model from 'Active' to 'In Closeout'.
12. Document Archiving (TASK_CREATE) | Create a task for the Project Admin to ensure all manuals, warranties, and as-built drawings are uploaded.
13. Create Final Project Report Entry (ENTRY_CREATE) | Create a summary entry in the Archive Data Model containing the final project metrics.
14. Generate Closeout Summary Report (REPORT_CREATE) | Generate a PDF report containing the final punch list resolution stats, total costs, and completion dates.
15. Send Final Handover Package (EMAIL) | Send an email to the Client containing the link to the Final Project Report and the completed Punch List.
16. Set Project Status to 'Closed' (ENTRY_UPDATE) | Update the Project Data Model status to 'Closed' to trigger the end of the project lifecycle.
17. Cleanup Temporary Work Orders (ENTRY_DELETE) | Delete temporary/adhoc work order entries that were only created for the duration of the punch list phase.
End (END) | End of the Workflow/Process