## Sheet1
Label | Value | Notes
Created by checklistguro.com
Pre-Meeting Preparation (STEP)
Review Project Proposal & Contract (TEXT)
Gather Relevant Project Documents (Drawings, Specifications, Permits) (UPLOAD)
Confirm Attendance Count (For Room/Platform Capacity) (NUMBER)
Confirm Date and Time of Meeting (DATE)
Choose Meeting Platform (In-Person, Zoom, Microsoft Teams, etc.) (SELECTION options: In-Person, Zoom, Microsoft Teams, Google Meet, Other)
Prepare Preliminary Agenda (TEXT)
Identify Key Stakeholders (Client, Architect, Engineer, Subcontractors) (SELECTION options: Client, Architect, Structural Engineer, MEP Engineer, General Contractor, Subcontractor 1, Subcontractor 2)
Meeting Logistics (STEP)
Meeting Location (Physical or Virtual) (LOCATION)
Meeting Start Time (DATE)
Number of Attendees Confirmed (NUMBER)
Meeting Platform (if virtual) (SELECTION options: Microsoft Teams, Zoom, Google Meet, Other)
Audio/Video Test Completed (if virtual) (SELECTION options: Yes, No)
Meeting Agenda (Uploaded) (UPLOAD)
Introductions & Roles (STEP)
Meeting Facilitator Name (TEXT)
Project Manager Name (TEXT)
Client Representative Name (TEXT)
Architect Name (TEXT)
General Contractor Name (TEXT)
Brief Introduction from Each Attendee (Role & Experience) (TEXT)
Confirm Roles Aligned with Project Organization Chart (SELECTION options: Yes, No, N/A)
Project Overview & Goals (STEP)
Project Description & Background (TEXT)
Project Goals - What are we trying to achieve? (TEXT)
Overall Project Budget (Estimated) (NUMBER)
Key Project Objectives (SMART Goals) (TEXT)
Project Delivery Method (e.g., Design-Bid-Build, Design-Build, CM at Risk) (SELECTION options: Design-Bid-Build, Design-Build, CM at Risk, Other)
Scope Inclusions (Brief Summary) (TEXT)
Scope Exclusions (What's NOT included?) (TEXT)
Communication & Reporting (STEP)
Preferred Communication Method (Primary) (SELECTION options: Email, Phone Call, Project Management Software (Specify), Instant Messaging (Specify))
Preferred Communication Method (Urgent Issues) (SELECTION options: Phone Call, Text Message, Instant Messaging (Specify))
Reporting Frequency (e.g., daily, weekly) (NUMBER)
First Progress Report Due Date (DATE)
Escalation Path for Issues (TEXT)
Project Management Software (SELECTION options: Procore, Autodesk Build, PlanGrid, Other (Specify))
Contact Person for Reporting Inquiries (TEXT)
Schedule & Milestones (STEP)
Review Project Start Date (DATE)
Confirm Project Duration (in days/weeks) (NUMBER)
Confirm Key Milestone 1 Target Date (DATE)
Confirm Key Milestone 2 Target Date (DATE)
Discuss Potential Schedule Constraints (e.g., weather, material lead times) (TEXT)
Schedule Review Frequency (Weekly/Bi-weekly/Monthly) (SELECTION options: Weekly, Bi-weekly, Monthly)
Estimate Float/Buffer Time for Potential Delays (in days) (NUMBER)
Review Critical Path Schedule (if available) (UPLOAD)
Risk & Issues Management (STEP)
Preliminary Risk Assessment Summary (TEXT)
Identified High-Level Risks (Select all that apply) (SELECTION options: Permitting Delays, Material Price Fluctuations, Labor Shortages, Unexpected Site Conditions, Weather Impacts, Design Changes, Subcontractor Performance)
Estimated Probability (1-10) for Top Risk (e.g., Permitting Delays) (NUMBER)
Estimated Impact (1-10) for Top Risk (e.g., Permitting Delays) (NUMBER)
Brief Mitigation Strategies Discussion for Top Risks (TEXT)
Risk Escalation Path (Primary Contact) (SELECTION options: Project Manager, Site Superintendent, Construction Director, Client Representative)
Date of Next Risk Review Meeting (DATE)
Next Steps & Action Items (STEP)
Identify and Assign Meeting Minutes Recorder (TEXT)
Brief Summary of Key Decisions Made (TEXT)
Immediate Follow-Up Items (Select all that apply) (SELECTION options: Confirm Project Schedule, Review and Approve Subcontractor List, Finalize Site Logistics Plan, Distribute Contact List, Confirm Insurance Certificates)
Assigned To (Follow-up Item 1) (TEXT)
Due Date (Follow-up Item 1) (DATE)
Assigned To (Follow-up Item 2) (TEXT)
Due Date (Follow-up Item 2) (DATE)
Post-Meeting Follow-Up (STEP)
Meeting Minutes Distribution Date (DATE)
Summary of Key Decisions & Action Items (Record for future reference) (TEXT)
Distribution List Confirmation (Confirm who received the minutes) (SELECTION options: Project Manager, Client, Superintendent, Key Subcontractors, Design Team)
Number of attendees who confirmed receipt of the meeting minutes (NUMBER)
Notes on any outstanding questions or issues requiring further clarification (TEXT)
Upload of meeting recording (if applicable) (UPLOAD)