## Sheet1
Label | Description
Created by checklistguro.com
Start (START) | Start of the Workflow/Process
1. Fetch Available Resources (ENTRY_GET) | Retrieve all personnel entries from the Resource Data Model where status is 'Available'.
2. Fetch Project Requirements (ENTRY_GET) | Retrieve the specific skill requirements and required hours from the Project Data Model.
3. Calculate Total Required Hours (ENTRY_AGGREGATE) | Sum the 'Required Hours' property from the Project Requirements entries to determine total workload.
4. Calculate Capacity Gap (CALCULATION) | Subtract 'Total Required Hours' from 'Total Available Resource Hours' to identify if more staff is needed.
5. Assign Resource Researcher (TASK_CREATE) | Create a task for the Resource Manager to match specific skills to the project needs.
6. Update Resource Status (ENTRY_UPDATE) | Update the status of a selected resource from 'Available' to 'Reserved' in the Resource Data Model.
7. Create Allocation Record (ENTRY_CREATE) | Create a new entry in the 'Allocations' Data Model linking the Resource, Project, and Date Range.
8. Calculate Total Allocated Cost (ENTRY_AGGREGATE) | Sum the 'Hourly Rate' of all resources assigned to this specific project entry.
9. Final Budget Review (TASK_CREATE) | Create a task for the Finance Controller to approve the cost of the allocated resources.
10. Notify Resource Manager (EMAIL) | Send an email to the Resource Manager with the summary of the new allocation.
11. Notify Assigned Staff (EMAIL) | Send an email to the assigned employee informing them of their upcoming project commitment.
12. Update Project Schedule (ENTRY_UPDATE) | Update the 'Resource Confirmed' checkbox in the Project Data Model to true.
13. Generate Allocation Utilization Report (REPORT_CREATE) | Create a report showing the percentage of resource utilization across all active projects.
14. Cleanup Draft Allocations (ENTRY_DELETE) | Delete any temporary or unapproved allocation entries created during the planning phase.
End (END) | End of the Workflow/Process