## 6a410eee8d045fc590b65f1b
Label	Description

Created by checklistguro.com

Start (START)	Start of the Workflow/Process
1. Initialize Project Record (ENTRY_CREATE)	Create a new entry in the Project Data Model to kick off the project lifecycle.
2. Define Project Scope (TASK_CREATE)	Assign a task to the Project Manager to define deliverables and constraints.
3. Create Milestone Entries (ENTRY_CREATE)	Generate individual entries in the Milestone Data Model based on the project roadmap.
4. Assign Milestone Owners (TASK_CREATE)	Create tasks for specific team members to take ownership of individual milestones.
5. Retrieve Project Milestones (ENTRY_GET)	Fetch all milestone entries associated with the current Project ID.
6. Calculate Total Project Duration (CALCULATION)	Calculate the difference between the Project Start Date and the Project End Date.
7. Get Milestone Statuses (ENTRY_GET)	Retrieve the completion status of all child milestones.
8. Calculate Percentage of Completion (ENTRY_AGGREGATE)	Aggregate completed milestones vs. total milestones to determine project progress percentage.
9. Sum Total Project Budget Spent (ENTRY_AGGREGATE)	Aggregate the 'Cost' property from all milestone entries to track total spend.
10. Review Milestone Progress (TASK_CREATE)	Create a recurring task for the Stakeholder to review milestone achievements.
11. Update Project Health Status (ENTRY_UPDATE)	Update the 'Health' field (Green, Amber, Red) in the Project Data Model based on progress.
12. Check Schedule Variance (CALCULATION)	Calculate the difference between the 'Planned End Date' and the 'Forecasted End Date'.
13. Notify Delay Alert (EMAIL)	Send an email to the Project Manager if the Schedule Variance calculation exceeds a specific threshold.
14. Mitigation Plan Creation (TASK_CREATE)	Create a task to develop a recovery plan if a milestone is flagged as 'Delayed'.
15. Generate Weekly Progress Report (REPORT_CREATE)	Create a visual report summarizing completed milestones, upcoming deadlines, and budget status.
16. Distribute Status Report (EMAIL)	Email the generated Project Progress Report to all project stakeholders.
17. Close Completed Milestone (ENTRY_UPDATE)	Update the status of a milestone entry to 'Completed' once all related tasks are finished.
18. Finalize Project Record (ENTRY_UPDATE)	Update the Project Data Model entry to 'Closed' upon achievement of the final milestone.
19. Urgent Deadline Alert (SMS)	Send an SMS to the Project Owner if a high-priority milestone enters a 'Critical' state.
End (END)	End of the Workflow/Process