## 6a410f708d045fc590b660d8
Label	Description

Created by checklistguro.com

Start (START)	Start of the Workflow/Process
1. Fetch Test Plan (ENTRY_GET)	Retrieve the approved Test Plan entry from the Test Management data model.
2. Initialize Test Cycle (ENTRY_CREATE)	Create a new Test Cycle entry to track the current testing execution period.
3. Identify Test Cases (ENTRY_GET)	Retrieve all Test Case entries associated with the specific Test Plan.
4. Assign Test Execution (TASK_CREATE)	Create a task for the QA Engineer to begin executing the identified test cases.
5. Update Test Case Status (ENTRY_UPDATE)	Update the status of individual Test Case entries to 'In Progress' or 'Passed/Failed'.
6. Log Defect (ENTRY_CREATE)	Create a new Defect/Bug entry when a test case fails.
7. Assign Bug Fix (TASK_CREATE)	Create a task for the Developer to investigate and resolve the logged defect.
8. Update Defect Status (ENTRY_UPDATE)	Update the Defect entry status to 'Resolved' once the fix is implemented.
9. Verify Fix (ENTRY_GET)	Retrieve the linked Defect entry to trigger re-testing.
10. Regression Testing Task (TASK_CREATE)	Create a task for QA to perform regression testing after the bug fix is deployed.
11. Calculate Pass/Fail Rate (ENTRY_AGGREGATE)	Aggregate Test Case entries to calculate the percentage of passed vs. failed tests.
12. Sum Total Defects (ENTRY_AGGREGATE)	Aggregate Defect entries to count the total number of open vs. closed bugs.
13. Calculate Test Coverage Score (CALCULATION)	Execute a formula comparing executed test cases against total planned test cases.
14. Generate QA Summary Report (REPORT_CREATE)	Create a summary report containing the aggregated pass/fail metrics and defect counts.
15. Notify Stakeholders of Failure (EMAIL)	Send an email to the Project Manager and Product Owner if the failure rate exceeds a threshold.
16. Send Completion Alert (EMAIL)	Send an email to the Release Manager when the Test Cycle is marked as 'Completed'.
17. Finalize Test Cycle (ENTRY_UPDATE)	Update the Test Cycle entry status to 'Closed' or 'Finished'.
18. Cleanup Draft Test Cases (ENTRY_DELETE)	Delete any temporary or draft Test Case entries that were not part of the official execution.
End (END)	End of the Workflow/Process