## 6a410f1b8d045fc590b65fb6
Label	Description

Created by checklistguro.com

Start (START)	Start of the Workflow/Process
1. Identify Asset/Process (ENTRY_GET)	Retrieve existing entries from the Asset/Process Data Model to define the scope of the assessment.
2. Initialize Risk Assessment Record (ENTRY_CREATE)	Create a new entry in the Risk Assessment Data Model to track this specific assessment instance.
3. Conduct Risk Identification (TASK_CREATE)	Assign a task to the Risk Officer to identify potential threats and vulnerabilities.
4. Log Identified Risks (ENTRY_UPDATE)	Update the Risk Assessment entry with the list of identified threats and their initial descriptions.
5. Assess Impact and Likelihood (TASK_CREATE)	Assign a task to subject matter experts to rate the probability and impact of each identified risk.
6. Record Risk Scores (ENTRY_UPDATE)	Update the Risk entries with numeric values for Likelihood and Impact scores.
7. Calculate Risk Score (CALCULATION)	Execute formula (Likelihood * Impact) to determine the Risk Magnitude for each entry.
8. Calculate Total Risk Exposure (ENTRY_AGGREGATE)	Aggregate all risk scores to find the maximum risk level currently present in the assessment.
9. Develop Mitigation Plan (TASK_CREATE)	Assign a task to the Department Head to define actions for risks scored above the acceptable threshold.
10. Log Mitigation Strategies (ENTRY_UPDATE)	Update the Risk entries with specific mitigation actions, owners, and deadlines.
11. Retrieve Risk Register (ENTRY_GET)	Fetch all identified risks and their mitigation status for final review.
12. Final Risk Approval (TASK_CREATE)	Assign a task to the Risk Committee/Manager to review and approve the assessment results.
13. Notify Stakeholders of Approved Risk Plan (EMAIL)	Send an email to all Department Heads containing the finalized Risk Assessment summary.
14. Generate Risk Assessment Report (REPORT_CREATE)	Create a formal PDF/Report summarizing the findings, scores, and mitigation steps for compliance records.
15. Finalize Assessment Status (ENTRY_UPDATE)	Update the Risk Assessment entry status to 'Completed' and timestamp the closure.
End (END)	End of the Workflow/Process