## 6a410ef28d045fc590b65f2b
Label	Description

Created by checklistguro.com

Start (START)	Start of the Workflow/Process
1. Retrieve Project Site Details (ENTRY_GET)	Fetch the specific site information, location, and project scope from the Project Data Model.
2. Create Mobilization Record (ENTRY_CREATE)	Initialize a new 'Mobilization Log' entry to track the progress of the setup process.
3. Assign Site Supervisor (TASK_CREATE)	Create a task for the Site Supervisor to review the mobilization checklist.
4. Fetch Required Equipment List (ENTRY_GET)	Retrieve the list of heavy machinery and tools required for the specific site from the Equipment Data Model.
5. Equipment Logistics Coordination (TASK_CREATE)	Assign a task to the Logistics Manager to arrange delivery of the retrieved equipment.
6. Update Equipment Status (ENTRY_UPDATE)	Update the status of identified equipment entries to 'In Transit' or 'Reserved'.
7. Permit and Compliance Check (TASK_CREATE)	Create a task for the Safety Officer to verify all local site permits are valid.
8. Get Subcontractor Contact Info (ENTRY_GET)	Retrieve contact details for assigned subcontractors from the Vendor Data Model.
9. Notify Subcontractors (EMAIL)	Send an email to all relevant subcontractors with the site arrival schedule and safety protocols.
10. Create Site Safety Plan (ENTRY_CREATE)	Generate a new 'Site Safety Plan' entry specific to this site location.
11. Calculate Mobilization Budget (CALCULATION)	Sum the estimated costs of equipment, labor, and permits to calculate total mobilization cost.
12. Aggregate Equipment Costs (ENTRY_AGGREGATE)	Sum the rental costs of all equipment entries selected for this site.
13. Site Container/Office Setup (TASK_CREATE)	Assign a task to the Facilities Team to install temporary site offices and containers.
14. Update Site Readiness Status (ENTRY_UPDATE)	Update the main Project entry to 'Mobilization In Progress'.
15. Alert Site Crew (SMS)	Send an SMS to the site crew with the mobilization start date and time.
16. Final Site Inspection (TASK_CREATE)	Create a final task for the Project Manager to verify all setup tasks are completed.
17. Generate Mobilization Completion Report (REPORT_CREATE)	Create a summary report containing all completed tasks and finalized costs for stakeholder review.
18. Set Site Status to 'Active' (ENTRY_UPDATE)	Update the site entry status to 'Active' once the inspection is successfully completed.
End (END)	End of the Workflow/Process