## Sheet1
Label | Description
Created by checklistguro.com
Start (START) | Start of the Workflow/Process
1. Fetch Product Backlog (ENTRY_GET) | Retrieve all user stories and bugs from the Backlog Data Model that are marked as 'Ready for Sprint'.
2. Calculate Total Story Points (ENTRY_AGGREGATE) | Sum the 'Estimate' property of all selected backlog entries to determine total workload.
3. Calculate Sprint Capacity (CALCULATION) | Calculate the available development hours by subtracting meeting time from total working hours.
4. Determine Sprint Load Ratio (CALCULATION) | Divide Total Story Points by Sprint Capacity to check if the sprint is over-capacity.
5. Create Sprint Record (ENTRY_CREATE) | Create a new entry in the 'Sprints' Data Model with the calculated start and end dates.
6. Assign Sprint Planning Meeting (TASK_CREATE) | Create a task for the Product Owner and Scrum Master to conduct the official planning session.
7. Create Sprint Backlog Tasks (TASK_CREATE) | For every selected backlog item, create a corresponding 'Development Task' assigned to the team.
8. Define Definition of Done Checklist (TASK_CREATE) | Attach a standard 'Definition of Done' checklist to all newly created development tasks.
9. Update Backlog Status (ENTRY_UPDATE) | Update the status of the retrieved backlog entries from 'Ready for Sprint' to 'In Sprint'.
10. Link Tasks to Sprint (ENTRY_UPDATE) | Update all selected backlog entries to associate them with the newly created Sprint ID.
11. Notify Engineering Team (EMAIL) | Send an email to the development group with the summary of the new Sprint goals and scope.
12. Generate Sprint Forecast Report (REPORT_CREATE) | Create a report visualizing the total points vs. capacity for the upcoming sprint.
13. Create Sprint Ceremony Calendar Event (ENTRY_CREATE) | Create a calendar entry for the Daily Standup, Sprint Review, and Retrospective.
End (END) | End of the Workflow/Process