## Sheet1
Label | Description
Created by checklistguro.com
Start (START) | Start of the Workflow/Process
1. Retrieve Stakeholder List (ENTRY_GET) | Fetch all active stakeholders and their contact details from the Stakeholder Data Model.
2. Fetch Project Milestones (ENTRY_GET) | Retrieve upcoming milestones and completion status from the Project Progress Data Model.
3. Calculate Total Budget Spent (ENTRY_AGGREGATE) | Sum all 'Actual Cost' entries from the Expense Data Model to compare against the budget.
4. Calculate Variance Percentage (CALCULATION) | Calculate the percentage difference between the Budgeted Cost and the Actual Cost retrieved from the aggregation.
5. Create Monthly Progress Report Entry (ENTRY_CREATE) | Create a new record in the 'Reports' Data Model containing the aggregated metrics and period dates.
6. Assign Report Review Task (TASK_CREATE) | Create a task for the Project Manager to review the generated report data for accuracy.
7. Update Milestone Status (ENTRY_UPDATE) | Update the 'Last Reported Date' in the Project Milestone Data Model to reflect the current reporting cycle.
8. Generate PDF Stakeholder Report (REPORT_CREATE) | Generate a formal, formatted report document using the data from the newly created Report Entry.
9. Distribute Report via Email (EMAIL) | Send the generated PDF report and a summary of key metrics to the email addresses retrieved in the Stakeholder List.
10. Send Critical Alert SMS (SMS) | Send a brief SMS notification to high-priority stakeholders if the Variance Percentage calculation exceeds a predefined threshold.
11. Log Communication Activity (ENTRY_CREATE) | Create an entry in the 'Communication Log' Data Model to document that the reporting process was completed.
12. Schedule Follow-up Meeting (TASK_CREATE) | Create a task for the Account Manager to schedule a meeting if the report contains 'Red' status flags.
End (END) | End of the Workflow/Process