## 6a410ee28d045fc590b65ef5
Label	Description

Created by checklistguro.com

Start (START)	Start of the Workflow/Process
1. Retrieve Dam Sensor Data (ENTRY_GET)	Fetch the latest readings from piezometers, inclinometers, and settlement markers from the Monitoring Data Model.
2. Calculate Pore Pressure Ratio (CALCULATION)	Calculate the ratio of pore water pressure to total overburden pressure to check for stability thresholds.
3. Calculate Rate of Displacement (CALCULATION)	Determine the velocity of movement by comparing the current displacement reading against the previous reading.
4. Update Sensor Threshold Status (ENTRY_UPDATE)	Update the 'Status' field in the Sensor Data Model to 'Alert' or 'Critical' if thresholds are breached.
5. Aggregate Weekly Precipitation (ENTRY_AGGREGATE)	Sum all rainfall entries from the last 7 days to calculate cumulative rainfall loading on the dam crest.
6. Create Incident Report (ENTRY_CREATE)	Automatically generate a new entry in the Incident Log Data Model when a threshold breach is detected.
7. Assign Site Inspection Task (TASK_CREATE)	Create a task for the Geotechnical Engineer to perform a physical visual inspection of the containment area.
8. Create Maintenance Work Order (TASK_CREATE)	Generate a task for the maintenance team to inspect the spillway and drainage systems.
9. Notify Emergency Response Team (EMAIL)	Send an urgent email alert to the Emergency Response Team (ERT) and Site Manager containing the breach details.
10. Send Critical Alert SMS (SMS)	Send an SMS notification to the Safety Officer for immediate attention to high-risk movement readings.
11. Fetch Inspection Checklists (ENTRY_GET)	Retrieve the predefined safety checklist template associated with the current dam section.
12. Generate Monthly Compliance Report (REPORT_CREATE)	Compile all sensor data, inspection results, and incident logs into a formal Monthly Monitoring Report.
13. Update Dam Health Score (ENTRY_UPDATE)	Update the overall 'Health Index' in the Asset Registry based on the aggregated monitoring results.
14. Archive Old Sensor Logs (ENTRY_DELETE)	Remove or move expired/redundant raw sensor readings from the active monitoring model to historical storage.
End (END)	End of the Workflow/Process